## Text
Project Name |  | Project Name | [6 empty] | Project Code |  | YY-0001
Project Manager |  | Name of Project Lead | [6 empty] | Project Sponsor |  | Name of Sponsor
Current Phase |  | Delivery | [6 empty] | Planned Close Date |  | 2021-08-31 |  | Guidance for Use
Date of Report |  | 2021-02-23 | [10 empty] | Currently this report is to be completed on a monthly basis for:
Project Summary | [13 empty] | 1. Lite Projects in the Delivery phase but not using a project lite workbook
A short description of what the project will achieve | [13 empty] | 2. Full projects
If already completing the status report in a project lite workbook, you do not need to fill in this report at this time.
|  | Deliverables | Time | Resources | Risks | Scope | Budget | Benefits |  | Overall Project RAG |  |  | Use the text drop-down menus to change RAG statuses. Then also allocate an overall RAG status to your project. The Information button links to RAG status guidance.
|  | Amber | Red | Green | Green | Green | Green | Green |  | Amber
|  | 3 | -1 | 5 | 5 | 5 | 5 | 5 |  |  |  |  | The milestone date fields will flag if date has passed and the status is not complete. Additionally, the planned close date will flag if that date has passed, indicating that an exception report is required.
Period Highlights & RAG Rationale |  | Highlights: notable activities during the reporting period, positive or negative
RAG Rationale: Reason for overall RAG status and any supporting information about individual RAG statuses that may be necessary. All red RAG statuses should be detailed here
Where necessary, insert lines if more milestones or more main risks required to be added.
Guidance on Risk Categorisation can be found using the information button above the category column.
Milestones | [5 empty] | Dates | Status |  | Comments |  |  |  | Do not remove any fields in the sheet.
PID/Framing | [5 empty] | 2021-02-01 | Complete |  | Investigate requirements, procurement, budget
PID | [5 empty] | 2021-02-01 | Complete | [5 empty] | Text in the Milestones and Comments area is to show an example only.
Build | Build |  |  |  |  | 2021-02-26 | In progress |  | Expect to have system migrated by end of month
Go Live | [5 empty] | 2021-04-01 | Not Started |  | System required to be live for Trimester 3
Service Live | [5 empty] | 2021-05-01 | Not Started |  | Support coverage to begin once system live and stable
Close | [5 empty] | 2021-08-01 | Not Started
Main Risks & Issues
ID | Title/Description | [8 empty] | Category | Status | Owner
R01 | High level Risk Title/Description | [8 empty] | Cost | Open
Text in the 2nd Risk line is to show an example only

## drop downs (hidden)
Phase | Milestone Status | Risk Status | Risk Category | RAG
Pre Brief | Not Started | Open | Cost | Red
Initiation | In progress | Mitigated | Schedule | Amber
Delivery | Complete | Escalated | Scope | Green
Handover to Support |  | Closed | Quality
Closing |  |  | Security
Customer Experience
Compliance

## Visual (hidden)
Project Name |  | vSoC Rebuild & Transition to IS | [6 empty] | Project Code |  | 21-0005
Project Manager |  | Stacy Robb | [6 empty] | Project Sponsor |  | Michael Greenhalgh
Current Phase |  | Delivery | [6 empty] | Planned Close Date |  | 2021-08-31
Date of Update |  | 2021-02-23
Project Summary
This project will deliver new and up-to-date infrastructure for the current system and network hosting the virtual school of computing (vSoC), as well as improve the capacity and monitoring of the system. It will also focus on developing a supported service for the vSoC within IS
|  | Deliverables | Time | Resources | Risks | Scope | Budget | Benefits
Period Highlights & RAG Rationale |  | Highlights: PID and Plan complete, requirements going to project Board for sign off.
RAG Rationale: IS do not have the knowledge currently required to ensure that the solution design is both state of the art and also meets the future demands of the system. Furthermore, budgetary requirements remain difficult to pin down as we are still working out current (and potential) usage requirements and the impact of these requirements on hardware needs. Additionally, there are discrepancies amongst the business owners as to what requirements should be prioritised and when.
Milestones | [5 empty] | Dates | Status |  | Comments
PID/Framing | [5 empty] | 2021-02-01 | Complete |  | Investigate requirements, procurement, budget
PID | [5 empty] | 2021-02-01 | Complete
Build | Build |  |  |  |  | 2021-02-26 | In progress |  | Expect to have system migrated by end of month
Go Live | [5 empty] | 2021-04-01 | Not Started |  | System required to be live for Trimester 3
Service Live | [5 empty] | 2021-05-01 | Not Started |  | Support coverage to begin once system live and stable
Close | [5 empty] | 2021-08-01 | Not Started
Main Risks & Issues
ID | Title/Description | [8 empty] | Category | Status | Owner
R01 | Project staff unable to prioritise work on this project vs other projects | [8 empty] | Strategic/ Commercial | Open | Jen Moxey
R02 | Virus response may cause schools and nurseries to close, causing some project staff to be unable to dedicate time to project | [10 empty] | Stacy Robb
R03 | Staff have limited technical knowledge on subject matter and a consultant may require to be hired. There is no line in the budget for this | [10 empty] | Iain Russell
Amber
Note on E10: Robb, Stacy: To update the RAG Status, select the icon, then right click and choose 'Fill' to format. These should only be filled Red, Amber or Green
Note on N10: Robb, Stacy: To update RAG status: click the box and type the colour name (Red, Amber, Green) and then change the colour to match