## Table of contents
More detail about the information presented in this document can be found in the accompanying Word Document file titled: Edinburgh Napier University Environmental Sustainability Team Communication Strategy Plan
Table of Contents
Steps
1 | Before promotion/ event planning
1.a | Events 2015-2016 | The purpose of this sheet is to clearly outline all the dates for events occurring during the academic year 2014/2015.
2 | Preparation for promotion/ events
2.a | Event Planning Steps | The steps and timeline that before planning a small to medium sized event. Info about material promotion is also included.
2.b | Communication Options | The table presented in this sheet presents all the potential communication options available to the Environmental Sustainability Team
2.c | EMS ref and Description of events | EMS Aspects Register linked to Engagement Strategies that will be used to promote the topics and brief descriptions of all the events taking place at the University as led by the Team are outlined here.
2.d | Hints and tips | Lessons learned, hints for the future and tips to achieve greater levels of success for communication are available here.
3 | Organisation after promotion/ events
3.a | Communication Evidence | For each given academic year, this sheet will show all the communication options used for each event.
3.b | Lessons and future ideas | All lessons learned from the events and activities that have taken place between October 2014 and September 2015 are outlined here and ideas for future work will also be described
3.c | Useful resources and links | Useful resources and links that can be shared through promotion are listed here.
4.a | Events 2016-2017 | The purpose of this sheet is to clearly outline all the dates for events occurring during the academic year 2015/2016.
4.b | Events 2017-2018 | The purpose of this sheet is to clearly outline all the dates for events occurring during the academic year 2016/2017.
5.a | OLD Events 2014-2015 | The purpose of this sheet is to clearly outline all the dates for events occurring during the academic year 2017/2018.
Updated Versions of this report
| Date last updated | Version number | Notes
| 2015-03-12 | 1 | Minor changes made
| 2015-03-18 | 1 | Minor changes made
| 2015-04-02 | 1 | Minor changes made
| 2015-05-11 | 1 | Minor changes made
| 2015-06-23 | 1 | Minor changes made
| 2015-07-03 | 2 | Significant changes made
| 2015-08-24 | 2 | Minor changes made
| 2015-10-01 | 2 | Minor changes made

## 1.a Events 2015-2016
| Event Planner 2015/2016 Academic Year |  | 2017-07-20 | All plan start dates pre-set to begin three weeks before actual start date. Except for some single day events (shorter pre-set time) and some important dates (longer -pre-set time).
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | EVENT DURATION | time axis 2015-08-13 to 2016-09-29
Sept | Trimester 1 |  |  | 2015-09-07 | 103
Sept | Organic September | 2015-08-20 | 12 | 2015-09-01 | 30
Sept | Cycle to Work Day 2015 | 2015-08-24 | 10 | 2015-09-03 | 1
Sept | Freshers Fair and Inductions | 2015-07-14 | 53 | 2015-09-05 | 14
Sept | eCycle launch | 2015-08-20 | 16 | 2015-09-05 | 14
Sept | Pedal for Scotland |  |  | 2015-09-06 | 1
Sept | National Fitness Day | 2015-08-03 | 37 | 2015-09-09 | 1
Sept | Rosh Hashanah (Jewish New Year) |  |  | 2015-09-13 | 2
Sept | European Mobility Week | 2015-08-26 | 21 | 2015-09-16 | 7
Sept | Car Free Day (In Town Without My Car) | 2015-09-01 | 21 | 2015-09-22 | 1
Sept | Eid al-Adha |  |  | 2015-09-22 | 2
Sept | Yom Kippur (Day of Atonement) |  |  | 2015-09-23 | 1
Oct | Liftshare week | 2015-09-14 | 21 | 2015-10-05 | 7
Oct | Muharram |  |  | 2015-10-13 | 1
Oct | Energy Saving week | 2015-10-05 | 21 | 2015-10-26 | 7
Oct | Halloween |  |  | 2015-10-31 | 1
Nov | All Saints' Day |  |  | 2015-11-01 | 1
Nov | Disruption Innovation Festival (online) |  |  | 2015-11-02 | 19
Nov | Bonfire night |  |  | 2015-11-05 | 1
Nov | National Commute Smart Week | 2015-10-19 | 21 | 2015-11-09 | 7
Nov | Remembrance Day |  |  | 2015-11-11 | 1
Nov | Diwali |  |  | 2015-11-11
Nov | European Week for Waste Reduction | 2015-10-26 | 26 | 2015-11-21 | 9
Nov | BHF collection | ? |  | ?
Nov | UK Road Safety Week | 2015-11-02 | 21 | 2015-11-23 | 7
Nov | First Sunday of Advent |  |  | 2015-11-29 | 1
Nov | St Andrew’s Day |  |  | 2015-11-30 | 1
Dec | Christmas switch off | 2015-11-03 | 28 | 2015-12-01 | 21
Dec | World AIDS Day | 2015-11-24 | 7 | 2015-12-01 | 1
Dec | Hanukkah |  |  | 2015-12-06 | 8
Dec | Assessment week |  |  | 2015-12-07 | 12
Dec | Christmas holidays |  |  | 2015-12-21 | 14
Jan | Mawlid al-Nabi |  |  | 2016-01-02 | 1
Jan | eCycle mid-year Launch | ? |  | ?
Jan | Inter Trimester Week |  |  | 2016-01-05 | 5
Jan | Trimester 2 |  |  | 2016-01-11 | 117
Jan | Environmental Network | 2015-12-16 | 34 | 2016-01-19 | 3
Jan | NSS Survey time |  |  | ?
Jan | Burns' Night |  |  | 2016-01-25 | 1
Jan | Work from Home Week | ? |  | ? | 7
Feb | World Cancer Day |  |  | 2016-02-04 | 1
Feb | Go Green Week | 2016-01-05 | 34 | 2016-02-08 | 7
Feb | Ash Wednesday |  |  | 2015-02-10
Feb | Valentine's Day |  |  | 2016-02-14 | 1
Feb | Shrove (Mardi Gras) |  |  | 2016-02-17 | 1
Feb | Chinese New Year |  |  | 2016-02-19 | 1
Feb | World Day of Social Justice |  |  | 2016-02-20 | 1
Feb | Fairtrade Fortnight | 2016-02-01 | 28 | 2016-02-29 | 13
March | St David’s Day |  |  | 2016-03-01 | 1
March | Love to Ride | 2016-02-16 | 14 | 2016-03-01 | 21
March | Zero Discrimination Day |  |  | 2016-03-01 | 1
March | World Wildlife Day | 2016-02-25 | 7 | 2016-03-03 | 1
March | Pass it on week | 2016-02-01 | 33 | 2016-03-05 | 7
March | International Women's Day |  |  | 2016-03-08 | 1
March | St.Patrick's Day |  |  | 2016-03-17 | 1
March | Palm Sunday |  |  | 2016-03-20
March | International Day of Happiness |  |  | 2016-03-20 | 1
March | Easter Break |  |  | 2016-03-21 | 13
March | International Day for the Elimination of Racial Discrimination |  |  | 2015-03-21 | 1
March | World Water Day | 2016-03-15 | 7 | 2016-03-22 | 1
March | Holi Day |  |  | 2016-03-23 | 1
March | Good Friday |  |  | 2016-03-25 | 1
March | Earth Hour | 2016-03-04 | 22 | 2016-03-26 | 1
March | Easter Sunday |  |  | 2016-03-27 | 1
April | Bowel cancer awareness month |  |  | 2016-04-01 | 30
April | April Fools' Day |  |  | 2016-04-01 | 1
April | World Health Day |  |  | 2016-04-07
April | John Muir Day |  |  | ?
April | Addressing Anxiety- Disrupting Negative thoughts |  |  | ?
April | Allergy Awareness Week | 2016-03-30 | 21 | 2016-04-20 | 6
April | Passover |  |  | 2016-04-22 | 8
April | Earth Day | 2016-04-01 | 22 | 2016-04-22 | 1
April | St. George's Day |  |  | 2016-04-23 | 1
April | Assessment week |  |  | 2016-04-25 | 12
May | National Walking Month | 2016-04-04 | 27 | 2016-05-01 | 31
May | May (Labour) Day |  |  | 2016-05-01 | 1
May | Beltane |  |  | 2016-05-01 | 1
May | BHF clothing collection | ? |  | ?
May | Clean Europe Day | ? |  | ? | 1
May | Inter Trimester Week |  |  | 2016-05-08 | 7
May | Walk to work week | ? |  | ? | 7
May | Green Office Week | ? |  | ? | 7
May | Mental Health Awareness Week | 2016-04-21 | 21 | 2016-05-12 | 7
May | Pentecost (Whitsunday) |  |  | 2016-05-15 | 1
May | Trimester 3 |  |  | 2016-05-16 | 103
May | Health Promotion Day | ? |  | ?
May | Student move-out from accommodation | ? |  | ?
May | Work Wise Week | ? |  | ?
May | National Commute Smart Week | ? |  | ?
June | Slowfood week | ? |  | ?
June | National Work from Home Day | ? |  | ?
June | World Environment Day | 2016-05-16 | 20 | 2016-06-05
June | Global Sharing week | ? |  | ?
June | First Day of Ramadan |  |  | 2016-06-06
June | World Oceans Day | 2016-05-18 | 21 | 2016-06-08 | 1
June | Shavuot (Hebrew Pentecost) |  |  | 2016-06-12
June | Green Transport Week | ? |  | ?
June | Bike Week | ? |  | ?
June | The Queen’s Official Birthday |  |  | 2016-06-13 | 1
June | Diabetes Week | ? |  | ?
June | Flag Day | ? |  | ?
June | EU Sustainable energy week | ? |  | ?
June | National Ride to Work Week | ? |  | ?
June | Men's health week | ? |  | ?
June | Communication Skills for Collaboration | ? |  | ?
June | Summer solstice |  |  | 2016-06-21
June | Recycling Week with Zero Waste Scotland | ? |  | ?
June | Catch the bus week | ? |  | ?
July | Eid al-Fitr |  |  | 2016-07-05
July | Information Overload - How to disconnect. | ? |  | ?
Aug | Assessment week |  |  | 2016-08-15 | 12
Aug | Strategies for Multigenerational caregiving | ? |  | ?
Aug | Meat Free Week | 2016-07-01 | 31 | 2016-08-01 | 7
Aug | eCycle Launch | ? |  | ?
Please visit this page for the EMS reference numbers: http://staff.napier.ac.uk/services/facilities/sustainability/managementprogrammes/Pages/EnvironmentalManagementSystem.aspx
University wide (Bold, Arial, 12, University Red: PANTONE 200 C)
Global, UN (Bold, Arial, 12, Green)
European (Bold, Arial, 12, Blue) | bar: 2015-08-29 to 2015-08-30
National (UK/ Scotland) and Local (Edinburgh region) (Bold, Arial, 12, Orange) | bar: 2015-08-29 to 2015-08-30
Non Env Sust related (Italic, Arial 10, no colour) | bar: 2015-08-29 to 2015-08-30

## 2.a Event planning steps
Promotion and event planning steps
2017-07-20
Steps to plan an event
| Name | Things to consider: (Note, this varies based on the size of the event, the figures below are averages for small to medium sized events)
| Create an event form (template in S drive) | 5+ weeks beforehand
| Fill it with the necessary details: Date, time, location, number of attendees/participants, size of room needed, catering ect | 5+ weeks beforehand
| Book the room (if necessary) | 5+ weeks beforehand
| Book parking spaces (if necessary) | 5+ weeks beforehand
| Create promotional material | 4+ weeks beforehand
| Send out promotional material | 4 weeks beforehand with reminders just before
Obtain communication evidence before and after the event
| Record lessons and tips for the future | After the event
Send out promotional material continued
Create posters or other fun notice
Put posters up at all campuses
Send posters in internal mail to campus managers
Put on Twitter and Facebook as posts and possibly as headers
| Send to EdNapNews | For lift, intranet news, ect
| Send to Enquiries | For MyNapier
| Put up on digital signage | For TV screens
Check out other options in 'communication options' tab
5 weeks before
4 weeks before
Before and after the event

## 2.b Options
Communication Specifications and Options
2017-07-20 |  |  |  | Green filled boxes are Communication Options that students prefer as identified by Student and Academic Services
http://staff.napier.ac.uk/services/corporateaffairs/exchange/Pages/Resources.aspx
Channel |  | Options |  | Specifications, constraints and descriptions |  |  | Contacts (Internal) | E-mail | Links to resources in the S drive
|  | Name | Address or Location | In general | For events | For weekly communication
Electronic Options
Ref #
Twitter | 1.a | Sustainable Edinburgh Napier University | .@SustainableENU | No political themes Send out Tweets at times when the user is most likely in front of a computer screen. Weekends, breakfast times, lunchtimes, evenings are all good. Use Hootsuite to schedule. Having hastags and themes is effective for keeping track of the topics covered and helps readers connect to other organisations/people looking at similar subjects. Some monitoring websites: Twitter Analytics, Followerwonk, Twitonomy, Tweet details | Tweet regularily before the event. Start tweeting the news about the same time that physical communication goes up. Create Twitter header with promotional material as additional communication tool | The best time to Tweet is Thursday afternoon- Friday Morning so students have time to read before the weekend. It would be best to post some useful Sustainability related information before the weekend. Post Thursday afternoon/ Friday morning. Update every week, two different topics | Sustainability/Environmental Advisor or Sustainability Engagement Officer | Jamie | For all Social Media:
| 1.b | Edinburgh Napier University | .@EdinburghNapier | Good to include these groups (when relevant) in tweets so they can spread information. | Encourage this account to re-tweet | Encourage this account to re-tweet | External Relations & Communications (ERC) | Laurie Jones | Engagement Resources: \\napier-mail.napier.ac.uk\staff\Property and Facilities\Departmental Data\facserv\Sustainability\Communication\Engagement\Resources to share with staff and students
| 1.c | NSA | @napierstudents |  |  |  | External Relations & Communications (ERC) |  | Social Media material: S:\facserv\Sustainability\Communication\Social Media
| 1.d | Edinburgh Napier Library | @EdNapLib | [5 empty] | Guides and templates for making promotional material: S:\facserv\Sustainability\Communication\Promotional material (guides and templates for making)
| 1.e | Edin Napier IT Bytes | @EdNapITBytes
| 1.f | Napier Vbase | @NapierVBase |  |  |  | Napier Students Association | Joyce McAree
| 1.g | [EN] Gage Fitness | @engage_fitness |  |  |  | Property and Facilities Engage Manager | Kevin Wright
| 1.h | Support Ed Napier | .@supportEdNapier
| 1.i | Napier Fresher's '15 | .@NapierFreshers
| 1.j | Team Napier | @TeamNapier |  |  |  | Property and Facilities Engage Manager | Kevin Wright
Facebook | 2.a | Edinburgh Napier University Environmental Sustainability | bit.ly/ENU-SO16 | No political themes. 'Like' pages to get more views and 'share' posts by others to spread the name of the page. Send out posts at times when the user is most likely in front of a computer screen. Weekends, breakfast times, lunchtimes, evenings are all good. Use Hootsuite to schedule. Having #'s and themes is effective for keeping track of the topics covered and helps readers connect to other organisations/people looking at similar subjects. | Events are great to include on this page, especially if they have posters. Create Facebook header with promotional material as additional communication tool | Every week it would be good to put re-share some static information about the work that is done by the team such as: recycling. | Accomodation Officer | Susan Burgess
| 2.b | Edinburgh Napier University Student Accomodation | www.facebook.com/EdinburghNapierAccommodation | This page is great for sharing information with students who live in residence. | Events are great to include on this page, especially if they have posters. |  | External Relations & Communications (ERC) | Laurie Jones
| 2.c | Edinburgh Napier University | https://www.facebook.com/EdinburghNapierUniversity?fref=pb&hc_location=profile_browser | This page is good to send information to the wider Edinburgh Napier University audience. | It is useful to post information onto the main Edinburgh Napier University Environmental Sustainability page then have the other pages share, like or comment. |  | External Relations & Communications (ERC) | Laurie Jones
| 2.d | Edinburgh Napier University Students' Association | https://www.facebook.com/napierstudents?fref=pb&hc_location=profile_browser | Student orientated |  |  | Napier Students Association Student Engagement Officer | Greig Kelbie
| 2.e | [EN] Gage Fitness | https://www.facebook.com/engagefitness?fref=pb&hc_location=profile_browser | Fitness orientated |  |  | Property and Facilities Engage Manager | Kevin Wright
| 2.f | Team Napier | https://www.facebook.com/TeamNapier?fref=pb&hc_location=profile_browser | Athletic team orientated |  |  | Property and Facilities Engage Manager | Kevin Wright
| 2.g | Edinburgh Napier International | https://www.facebook.com/ENUinternational?fref=pb&hc_location=profile_browser | International student orientated
| 2.h | Edinburgh Napier University careers | https://www.facebook.com/EdinburghNapierUniversityCareers?fref=ts | Career help orientated
| 2.i | Enjoy (catering)
Pinterest | 3.a | Edinburgh Napier University Environmental Sustainability Team | https://uk.pinterest.com/environment0058/ | It may be helpful to 'pin' images of different ideas or events to get students to begin thinking about a topic. For example- liking 'pins' that cover topics such as re-use, recycling, re-making items ect would be great before Pass It On Week. |  |  | Sustainability Engagement Officer | Jamie
| 3.b | ResLife Pinterest | https://uk.pinterest.com/ENUResLife/ |  |  |  | Accomodation Officer | Susan Burgess
Website | 4.a | Environmental Sustainability Team Website (Staff intranet page) | bit.ly/ENU-SO3 | Mainly static information but anything can be included here. | Update 2-3 weeks before the event to ensure message absorption | Any kind of static weekly event can be included. | Sustainability/Environmental Advisor or Sustainability Engagement Officer | Jamie | For all Website material:
| 4.b | Edinburgh Napier University Internet Page | http://www.napier.ac.uk/Pages/home.aspx | General static information is usually included on this website. | Major events could be included here. | N/A | Sustainability/Environmental Advisor | Jamie | MyNapier Student portal: S:\facserv\Sustainability\Communication\MyNapier student portal
| 4.c | Edinburgh Napier University Staff Intranet | http://staff.napier.ac.uk/Pages/home.aspx | All staff News Lift signs | Update 2-3 weeks before the event to ensure message absorption | Any kind of static weekly event can be included. | Property and Facilities PA to Directorate | Nyree Mairs | Edinburgh Napier University brand guidelines S:\facserv\Sustainability\Communication\Edinburgh Napier Uni BRAND guidelines
| 4.d | Edinburgh Napier University MyNapier Environment Page www.my.napier.ac.uk/environment | www.my.napier.ac.uk/environment | •Banners •Full Newsarticle (up for 28 days) • Main page quick news box (1 of 3, short summaries of events, opportunities like awards) • Main page last newsbox (monthly theme news) • Calendar (very short summaries only of events) • ‘Filter services for your needs’ (4 boxes, short summaries of the work happening with the team) • Main pages, these remain static, so information placed here should be about updates. Not upcoming events Requirement: Send word document with all information from promotional material included so they can easily copy and paste the information to other places. For static pages Images Home Page Height: 330px Width: 920px Standard Page Height: 230px Width: 920px For creation of DS slides we normally use a combination of PowerPoint (with custom settings) and Adobe Creative Cloud. Unfortunately, you need to buy an Adobe CC license for each user & there is a significant expense when it comes to purchasing it. Thus if you haven’t used it before, it would be recommended to try the package first by either downloading a trial version or using one of the Macs available in the Merchiston Library or JKCC with Adobe C6 package available on them. Additionally, when creating any promotional material, it is essential that you comply with Edinburgh Napier brand guidelines & visual identity. When it comes to the triangle grid, there are two different ones, which you’ll have to ask ERC for as they have the source file. | Send information to enquiries@napier.ac.uk at minimum 1 week before an event, promotion, scheduled session Update 2-3 weeks before the event to ensure message absorption. Minimum 1 week in advance so they can put information into the weekly newsletter that goes out on Mondays. | Any kind of static weekly event can be included. | enquiries@napier.ac.uk • Academic and Business Relationship Manager, Information Services • PA to Directorate, Property and Facilities • Student Information Officer – 2921, d.rannoch@napier.ac.uk • Information Resources Officer – 2972, j.ross@napier.ac.uk For the team: Sustainability Engagement Officer To upload documents to the P&F page go to: https://staffworkplace.napier.ac.uk/Services/Facilities/propertyfacilitiesdigital/SitePages/Home.aspx?InitialTabId=Ribbon%2EListItem&VisibilityContext=WSSTabPersistence | Jamie
E-mail | 5.a | Environmental Sustainability Team main e-mail address | environment@napier.ac.uk | No permissions | No permissions | No permissions | Sustainability/Environmental Advisor | Jamie
| 5.b | Student HTML e-mail |  |  |  |  | Sustainability/Environmental Advisor | Jamie
| 5.c | Staff HTML e-mail |  | JP has permissions | JP has permissions | JP has permissions | Student services and enquiries@napier.ac.uk | Jamie
DIGITAL | 6.a | P&F Communicate E-newsletter |  | This communication method is updated monthly. Anything from static information to events can be included. Template available in S drive. | Events are great to include in this, especially if they have posters. | If there are any regular weekly events, they can also be included such as environmental organisation meetings (if students of Edinburgh Napier University choose to create such an organisation) | PA to Directorate, Property and Facilities and External Relations & Communications (ERC) | Nyree Mairs and Rachael Fraser | Digital Signage material: S:\facserv\Sustainability\Communication\Digital Signage
| 6.b | eCycle newsletter | Mailchimp campaign (Username: environment@napier.ac.uk, password: 6.b.29Sighthill) | Provide updates for the eCycle scheme and information for registration. Ensure wording is chatty, dates are correct and e-mail adresses are right. BCC all those to whom the e-mail will be sent. | Provide a brief summary of relevant cycling related events. | N/A | Sustainability/Environmental Advisor or Sustainability Engagement Officer | Jamie
| 6.c | Digital Signage (TV and computer screens) |  | Numerous and various locations around all three campuses – content guidelines need to be adhered to at all times, as well as copyright and photographic policy and legislation. Each school and services department ‘owns’ set individuals screens and times that they manage content for. As a result of this devolved approach to the management of the screens, each school and department has one or two staff identified as ‘content managers’. Images and pictures can be hyperlinked but this will cover the whole image. The images have to fit the size of the TV screens (16:9 ratio) there will be several screens for us to use, there will be different channels, showing different things, it is possible to schedule timings as well. Student and Academic services can also promote information, they have specific templates and layouts for their screens. These can be found in the S drive under: Sustainability-Communication-Student and Academic Services poster templates TV screens: 1920w X 1080h (px) this is the same as a 16:9 ratio. Or 50.8cm x 28.575cm Computer screens: For Students (send to IS): 800w X 600h (px) or 21.167cm x 15.875cm, 200kb or less, must have ENU logo and a ENU email adress and must be jpg, For Staff (send to ednapiernews) jpg, 1260x1024px, central area should be kept free of text and light colours to as to accommodate the "ctrl+alt+del" message, the bottom two corners should also be free for stand by buttons, content should be relevant to staff, must abide by uni brand guidelines, must include the University logo, must be simple and attractive with not too much information and with a call to action. | Quick release of information TV and computer screens: Give two weeks for information to be posted | This promotional method can be used to share static information about the team such as: bin label information, annual events and so on. | PA to Directorate, Property Facilities and External Relations & Communications (ERC) Information Services | P&F Nyree Mairs ERC/IDEA Rachael Fraser SAS Daniel Rannoch Justen Ross IS Emma Farthing-Sykes Helen MacDonough Joyce Templeton (Library) ER&C James Anderson Caroline Weintz P&F Nyree Mairs Louise Cunningham NSA Craig Reid Paul Mitchell ENBS David Russell SOC Tom Flint SEBS Stephen Paterson SACI Andrew O’Dowd SLSS Omar Dellal SNMSC Omar Dellal
| 6.d | Moodle |  |  |  | N/A
| 6.e | YouTube | Not yet created | This tool is good for sharing user manual type information. A lot of important descriptions about a certain subject such as the eCycles. | If a group of interested students develops, it would be good for them to share videos regarding events and other themes. | N/A | Sustainability/Environmental Advisor or Sustainability Engagement Officer | Jamie
| 6.f | Instagram |  |  |  |  | Sustainability/Environmental Advisor or Sustainability Engagement Officer | Jamie
| 6.g | Videos |  |  |  |  | Sustainability/Environmental Advisor or Sustainability Engagement Officer | Jamie
| 6.h | Text Messaging |  |  |  |  | Sustainability/Environmental Advisor or Sustainability Engagement Officer | Jamie
Physical Options- On-Site Promotions
Paper promotions | 7.a | A4 promotional posters | Sighthill | Post message in: Staff kitchens and printer rooms (~15 posters) Poster boards on floors 1-3 in the classroom corridors (~5 posters) The Student hub (1 poster) At the reception desk Till points Health and Wellbeing Lift Points (28) | At least three weeks in advance to message absorption. Especially when you requirepeople to book spaces. | N/A | Sustainability/Environmental Advisor; Student services and enquiries@napier.ac.uk; Faculty Operations Manager | s.nairn@napier.ac.uk | Guides and templates for making promotional material: S:\facserv\Sustainability\Communication\Promotional material (guides and templates for making)
| 7.b | A4 promotional posters | Craiglockhart | About (~5) posters Health and Wellbeing Lift Points (8) | At least three weeks in advance to message absorption. Especially when you requirepeople to book spaces. | N/A | Campus manager | l.condie@napier.ac.uk Room 3/27
| 7.c | A4 promotional posters | Merchiston | About (~5) posters for the campus NSA posterboards (~3-5 posters) At the reception desk Till points Health and Wellbeing Lift Points (15) | At least three weeks in advance to message absorption. Especially when you requirepeople to book spaces. | N/A | Campus manager | Billie O'Neill B51
| 7.d | A0 poster boards | Merchiston reception area | Foyer area AO size posters up to 11 spaces available. Size of an AO is: 841mm (W) by 1,189mm (h) | Send A0 size poster to Merchiston at least 2-4 weeks in advance. A0 size posters can be made in CANVA | N/A | Campus manager |  | Edinburgh Napier University brand guidelines: S:\facserv\Sustainability\Communication\Edinburgh Napier Uni BRAND guidelines
| 7.d | Message board in lift | All campuses | Different options | Updated Every Tuesday and Thursday. At least 1 week in advance | N/A | External Relations & Communications (ERC) | Rachael Fraser
| 7.e | Poster holders in toilets | All campuses | Ladies/Men’s Toilets – 3 Campuses (Student and Staff only areas) | Updated once a month. Long waiting list: Three to four months in advance, if not more. These book out quickly | N/A | External Relations & Communications (ERC) | These need to be booked in advance by emailing c.weintz@napier.co.uk and posters for these need to be supplied by the originator.
| 7.f | Table talkers | All campuses | Fairtrade Forum table talkers can be obtained for free from the Fairtrade forum website. | It is possible to create table talkers using Word. Simply put in the same image twice, rotate one and make sure there is some space at the bottom and top of the page. Then print the page onto thick paper, fold it in half and tape or glue the bottom layers together until a triangle is made. This is helpful to promote events where individuals are required to do something, such as a swish event. | N/A | Sustainability Engagement Officer | Jamie
| 7.g | Invitations | All campuses | A useful way to engage staff and students is to provide invitations to events. This was done for the Staff and student swish in March 2015 and hopefully it will encourage people to come to the event. It is a nice reminder, gives them something to keep and on a personal note I have received nothing but smiles and thank yous for this gesture. |  | N/A | Sustainability Engagement Officer | Jamie
| 7.h | Flyers or leaflets | All campuses | Sending out flyers to students can complement putting up posters. |  | N/A | Sustainability Engagement Officer | Jamie
| 7.i | Pamphlets | All campuses | Pamphlets help share a larger quantity of information than can be provided in a pamphlet or poster. Useful for post-workshop information sharing. For example: after the Basic Bicycle Maintenance workshop, Grease Monkey provided digital and physical pamphlets which were shared with attendees. This may help encourage future participation in events or help students continue using the knowledge gained during the event. |  | N/A | Sustainability Engagement Officer | Jamie
| 7.j | Bike tags | All campuses | Bicycle tags have been used in the past to spread information about a bicycle related event. They have been successful. The tags were credit card sized plastic covers with workshop information within, these were attached to bicycles with string. |  | N/A | Sustainability Engagement Officer | Jamie
| 7.k | Laminated posters in bicycle sheds | All campuses | It is useful to put up lamintaed posters in bicycle sheds to promote cycling related material. |  | N/A | Sustainability Engagement Officer | Jamie
| 7.l | Team promotion added to pre-existing University promotion . |  | Additions to pre-existing University promotion such as little stickers, or section of flyers/pamphlets/ leaflets ect for the Team.
During event promotion | 8.a | Re-useable pop up display board | The Vault 6.B.25 | The display board requires the velcro roll, tape does not work. | The pop up boards with informatiion are useful during events to showcase information about the team, events anything. | N/A | Sustainability Engagement Officer | Jamie
| 8.b | Stalls/ Booths |  | Stalls/ booths with informatiion are useful during events to showcase information about the team, events anything. |  | N/A | Sustainability Engagement Officer | Jamie
Other Options
Personal promotion | 9.a | Inductions (staff and student) |  |  |  |  | Sustainability/Environmental Advisor or Sustainability Engagement Officer | Jamie
| 9.b | Ambassadors |  |  |  |  | Sustainability/Environmental Advisor or Sustainability Engagement Officer | Jamie
| 9.c | Class shout outs |  |  |  |  | Sustainability/Environmental Advisor or Sustainability Engagement Officer | Jamie
| 9.d | Volunteers |  |  |  |  | Sustainability/Environmental Advisor or Sustainability Engagement Officer | Jamie
| 9.e | Class reps |  |  |  |  | Sustainability/Environmental Advisor or Sustainability Engagement Officer | Jamie
| 9.f | Training session |  |  |  |  | Sustainability/Environmental Advisor or Sustainability Engagement Officer | Jamie
| 9.g | Design Competition |  | This would be a good method to use for major events or changes to the team such as team re-branding. |  |  | Sustainability/Environmental Advisor or Sustainability Engagement Officer | Jamie
| 9.h | Interviews
| 9.i | Focus groups
| 9.j | Questionnaires
| 9.k | Meetups
| 9.l | Campus users groups
| 9.m | Awareness Events
| 9.n | Exhibitions
| 9.o | Road shows
| 9.p | Class visits | Edinburgh Napier University | It could be useful to have speakers go to different classes (pending approval from lecturers) instead of setting up meeting points and expecting people to arrive for a talk. This would have been a good option for the Fairtrade producer visit in March 2015.
| 9.q | Start a campaign |  | Idea obtained from Shona Irwine for Fresher's Fair 2015 National Fitness Day at Edinburgh Napier University
| 9.r | Enlist the help of bloggers
Other Options | 10.a | Prizes |  | Prizes are good ways to encourage participation from individuals. |  |  | Sustainability/Environmental Advisor or Sustainability Engagement Officer | Jamie
| 10.b | Maps |  |  |  |  | Sustainability/Environmental Advisor or Sustainability Engagement Officer | Jamie
| 10.c | Stickers (ex- floor) |  | Stickers placed on the floor to communicate the placement of different objects can be allowed sometimes, for example: waste bin location stickers at Bainfield or floor directional stickers at the Sighthill reception area. |  |  | Sustainability/Environmental Advisor or Sustainability Engagement Officer | Jamie
| 10.d | T-shirts |  |  |  |  | Sustainability/Environmental Advisor or Sustainability Engagement Officer | Jamie
| 10.e | Photocall |  |  |  |  | Sustainability/Environmental Advisor or Sustainability Engagement Officer | Jamie
| 10.f | Speakerphone shout-outs |  | Ideal for event promotion, inspiration taken from NSA election campaign 2015 | Be based in a reception area (any campus) and advertise an event or campaign |  | Sustainability/Environmental Advisor or Sustainability Engagement Officer | Jamie
| 10.g | Photography challenge |  |  |  |  | Sustainability/Environmental Advisor or Sustainability Engagement Officer | Jamie
| 10.h | Yik Yak (anonymous social media app) |  | Yik Yak is used by other groups at the University to keep track of general student thoughts during the school year. Use this tool with caution however, as explicit material may occur.
| 10.i | Radio
| 10.j | Feedback forms
| 10.k | Apps
| 10.l | Google + photo
| 10.m | Blog
| 10.n | Infographic
| 10.o | Photocollage
| 10.p | Coordinated dancing |  | Idea obtained from Shona Irwine for Fresher's Fair 2015 National Fitness Day at Edinburgh Napier University
| 10.q | Movement sessions, simple 5 minutes (‘wiggle it, waggle it, twerk it, work it – just DON’T sit on it’) |  | Idea obtained from Shona Irwine for Fresher's Fair 2015 National Fitness Day at Edinburgh Napier University
| 10.r | Run around to win a free coffee/tea/ Fairtrade chocolate |  | Idea obtained from Shona Irwine for Fresher's Fair 2015 National Fitness Day at Edinburgh Napier University

## 2.c EMS ref and descriptions
EMS Aspects Register linked to Engagement Strategies |  |  |  | Details on EMS aspects found in: Aspects Register (ENU-EMS-079)
2017-07-20
Activity area | Activity | Aspects |  | Event and their descriptions that apply to the EMS
|  | # | Name | Relevant aspects | Name | Description | Links | Tips and suggestions
Energy use | Use of electrical equipment | 1 | Use of electricity | 1 | Christmas Switch Off | This campaign promotes reduction of energy waste by encouraging staff and students in accomodation to turn off all non essential electronic equipment over the Christmas holidays. The reduction is then collected and data presented to the university to show how much has been saved or not saved in relation to other years. | bit.ly/ENU-SO3 | Promotional material located in: S:\facserv\Sustainability\Communication\Promotional material\EVENTS\Christmas posters 2014
| Use of heating, CHP and gas in laboratories | 2 | Use of gas | 1 | Earth Hour | Lights off event to raise awareness about climate change. The university can spread the news about this event. | http://www.earthhour.org/ | Promotional material available on the website.
| Use of air-conditioning | 3 | Use and storage of refrigeration gases | 1 | Energy Saving Week | Energy Saving Week is a good time for the university to help students take back control of energy bills at home. The Energy Saving Trust website provides information on energy saving measures, grants that may be available, renewable energy, competitions and a general array of information that can help students reduce your energy consumption and energy bills at home. The Sustainability Office internet pages provide more information on how to save energy whilst at the University. Small changes such as switching off unnecessary electrical items and lights does make a difference. | http://www.energysavingtrust.org.uk/ | Information for the event available on the website.
|  |  |  | 1 | Go Green Week | Go Green Week is People & Planet’s annual national week of climate action in schools, colleges and universities. Every February, students run a week of activities to raise awareness and demand stronger action to tackle the climate crisis. | http://peopleandplanet.org/gogreenweek | Resources available at: http://peopleandplanet.org/fossil-free/resources
|  |  |  | All | Green Office Week | A fantastic opportunity to make a positive difference to the environment in practical ways, including transport, energy and waste. | www.greenofficeweek.eu | Resources available on the website.
Transport | Use of fleet; intercampus, business, domestic and international travel | 4 | Use of fuel (owned vehicles) | 6,8,9 | Bike Week | Bike Week is the UK’s biggest mass participation cycling event. Bike Week 2015 takes place between 13th-21st June. | bikeweek.org.uk | Resources available on the website.
|  | 5 | Spills/leaks from vehicles | 6,8,9 | Car Free Day (In Town Without My Car) | Annual event which sees thousands of cities across European take part and highlight the positive effects of car free travel ( health, safety and environmental benefits). | www.etatrust.org.uk/2015/05/world-car-free-day-2015/ | Ideas available on the website
|  | 6 | Domestic business travel | 6,8,9 | Catch the bus week | Catch the Bus Week is a national celebration of the benefits of taking the bus | http://www.catchthebusweek.co.uk/ | Ideas available on the website
|  | 7 | International business travel | 6,8,9 | Cycle to Work Day | Cycle to Work Day is a national event, championed by multi gold medal winning Paralympic cyclist, Dame Sarah Storey, which aims to encourage everyone to take to two wheels and cycle to work for just one dayTo date over half a million miles have been ridden for Cycle To Work Day. | www.cycletoworkday.org/ | Participation prizes available on the website
|  | 8 | Staff day-to-day commute | 6,8,9 | eCycle scheme | The eCycles scheme is part of a larger membership called the Edinburgh FTH group.. eCycles are the four (current as of Jan 2015) electrically assisted pedal bicycles available for staff and students at the university. They are a project undertaken with Edinburgh Further and Higher Education Transport Group (EFHETG). The eCycle scheme should be promoted twice a year for the benefit of each new cohort of students (during the start of the year and for the New Year). |  | Resources available in the S drive: S:\facserv\Sustainability\eCycles
|  | 9 | Student term-time and day-to-day commute | 6,8,9 | European Mobility Week | This is a European festival promoting environmentally sensitive transport and raising awareness of the nuisances causes by the use of private cars in the city (Air, noise pollution, congestion etc). Good opportunity to promote active travel and public transport usage. | www.mobilityweek.eu | Resources available on the website.
|  |  |  | All | Go Green Week | See above | See above | See above
|  |  |  | All | Green Office Week | See above
|  |  |  | All | Green Transport Week | The aim is to raise awareness of the impact travel has on the environment and to make people think about the way they travel on every journey. | www.etatrust.org.uk/campaign/green-transport-week | Information for the event available on the website.
|  |  |  | 6,8,9 | Liftshare week | This is a national event promoted by the university to share the benefits of car sharing and encouraging more people to join car sharing schemes.
|  |  |  | 6,8,9 | National Commute Smart Week | Raising awareness of smarter working practices and how they can help to avoid the misery of commuting in the dark winter months. | www.workwiseuk.org/commutesmartweek/
|  |  |  | 6,8,9 | National Ride to Work Week | Raising awareness about the benefits of using motorcycles and scooters to commute to and from work on a regular basis. 19th June is National Ride to Work Day. | www.ridetowork.org.uk
|  |  |  | 4, 6, 8, 9 | National Walking Month | Every May, Living Streets encourage people to take to their feet and feel the benefits of walking. | www.livingstreets.org.uk/national-walking-month | Resources and competition (miles logging) online
|  |  |  | 6,8,9 | Pedal for Scotland | An annual charity event aimed at encouraging cycling and raising money for charity. The Glasgow to Edinburgh cycle provides a fun and active day out with colleagues, friends and family – a good opportunity to get a team of employees together to represent the organisation. | www.pedalforscotland.org | Information for the event available on the website.
|  |  |  | 6,8,9 | National Travelwise Week | ACT TravelWise is the UK’s premier network for all organisations working to promote sustainable travel. Travelwise is a national campaign that seeks to raise awareness of the role individuals, businesses and schools can play in helping to reduce pollution and congestion caused by cars. | www.acttravelwise.org | Resources available on the website.
|  |  |  | 6,8,9 | UK Road Safety Week | An annual community event aimed at inspiring people to promote road safety within their local community. | www.roadsafetyweek.org.uk | Resources available on the website.
|  |  |  | 6,8,9 | Walk to Work Week | This week is all about encouraging staff and students to walk to work as much as possible. | http://www.livingstreets.org.uk/walk-with-us/walking-and-work/walk-to-work-week | Resources and competition (miles logging) online
|  |  |  | 6, 7, 8, 9 | Work from Home Day | Promoting the benefits of home working to both individuals, businesses and the environment | www.workwiseuk.org/workwiseweek/ | Resources and information available on the website
|  |  |  | 6, 7, 8, 9 | Work from Home Week | Work from Home Week - the leading UK resource for people who currently work from home or are considering it and want a better balance in their work / home life. | www.workfromhome.co.uk | Resources and information available on the website
Waste | Production and storage of waste | 10 | Generation of mixed municipal waste, not reused or recycled | 13 | British Heart Foundation Clothing Collection | We are the nation's heart charity and the largest independent funder of cardiovascular research.. Your donations fund our pioneering research that will save lives. Last year the goods you donated to BHF shops raised over £31 million to help in the fight against heart disease. | https://www.bhf.org.uk | This campaign promotes reduction of energy waste by encouraging staff and students in accomodation to turn off all non essential electronic equipment over the Christmas holidays. The reduction is then collected and data presented to the university to show how much has been saved or not saved in relation to other years. May 2015 update: There have been issues with communication and uplifts from BHF (which can cause fire hazards). If this issue is not resolved, then the scheme will be discontinued for 2016.
|  | 11 | Production of chemical/solvent/ animal by-product or other hazardous waste | 13 | European Week for Waste Reduction | The European Week for Waste Reduction is an initiative aiming to promote the implementation of awareness-raising actions about sustainable resource and waste management during a single week. | http://www.ewwr.eu/en/project/main-features | Post images of bin labels on social media. Also, upload interesting links to waste reduction oriented websites. The location of bin images in S drive for ENU accommodation: facserv-sustainability-student accommodation-waste-communication-bin stickers. Re-use map: http://www.changeworks.org.uk/projects/edinburgh-charity-shop-and-reuse-map Ideas available on the website
|  | 12 | Production of clinical waste | 13 | Go Green Week | See above | See above | See above
|  | 13 | Waste recycling (including composting) | All | Green Office Week | See above
|  |  |  | 13 | Pass It On Week | Pass it on week is all about re-use. It’s a week dedicated to encouraging people to get involved in re-use activity of all shapes and sizes. It could be swapping, sharing, repairing, upcycling or buying second hand. Anyone can get involved, events can be big or small such as repair workshops, or Swishing. It is possible to register the event on the recycle for Scotland website (this website also has a host of information about different ideas, and provides toolkits). Recycle for Scotland is brought to you by Zero Waste Scotland. | http://www.recycleforscotland.com/re-use/pass-it-week-%E2%80%93-7th-15th-march | Develop plans for events and workshops (ideas: upcycling, repair, re-use, teaching skills) Lots of ideas and resources available on the website. Also, they hold a meeting beforehand for anyone who wants to run an event to be learn about all the resources and ideas before the day.
Water use | Use of water | 14 | Use of water | 14,15 | World Oceans Day | World Oceans Day has been unofficially celebrated every 8 June since its original proposal in 1992 by Canada at the Earth Summit in Rio de Janeiro, Brazil. It was officially recognized by the United Nations in 2008. Since then it has been coordinated internationally by The Ocean Project and the World Ocean Network with greater success and global participation each year.
| Generation of effluent | 15 | Generation of effluent | 14,15 | World Water Day | The day focuses attention on the importance of freshwater and advocates for the sustainable management of freshwater resources. This day was first formally proposed in Agenda 21 of the 1992 United Nations Conference on Environment and Development in Rio de Janeiro. In 1993, the first World Water Day was designated by the United Nations General Assembly and since, each year focuses on a different issue.
Use and storage of chemicals, oils, fuel and pesticides | Use and storage of oils for general maintenance | 16 | Leaks/spills of maintenance oil | All can be included | Go Green Week | See above | See above | See above
| Use and storage of oils for cooking | 17 | Leaks/spills of cooking oil
| Use and storage of chemicals | 18 | Leaks/spills of chemicals
| Use and storage of fuel | 19 | Leaks/spills of fuel
| Use and storage of pesticides | 20 | Leaks/spills of pesticides
Emissions to air | Use of fume cupboards | 21 | Emissions from fume cupboards | All can be included | Go Green Week | See above | See above | See above
| Use of dust hopper | 22 | Emissions from dust hopper
Biodiversity Management | Grounds maintenance/landscaping | 23 | Provision of natural habitats | 23,24,25 | John Muir Day | The John Muir Way, Scotland’s newest, coast-to-coast trail linking Muir’s birthplace in Dunbar to Helensburgh was opened last April. John Muir was born in Dunbar on 21 April 1838, before emigrating to the USA. His environmental campaigning helped change how people view nature. | http://www.snh.gov.uk/johnmuir2015 | The John Muir Way, Scotland’s newest, coast-to-coast trail linking Muir’s birthplace in Dunbar to Helensburgh was opened last April. John Muir was born in Dunbar on 21 April 1838, before emigrating to the USA. His environmental campaigning helped change how people view nature. Event information on website
|  | 24 | Planting of new plants / trees |  | Slow Food Week | Slow Food on Campus is a student-led initiative. This programme promotes and develops local food cultures related to all aspects of university life. | http://www.slowfood.org.uk/projects/our-projects/slow-food-on-campus/ | Information available on the website
|  | 25 | Grounds maintenance activity |  | World Environment Day | It was established by the United Nations General Assembly in 1972
[5 empty] | World Wildlife Day | Started in 2013
Procurement | Procurement of goods and services (including whole life impact) | 26 | Procurement of electrical and other equipment (e.g. IT and laboratory) | 28 | Fairtrade Fortnight | Fair Trade fortnight provides a specific time to celebrate and acknowledge the Fair Trade movement. The university will focus on promoting Fair Trade during this time through various events, posters and possibly a visit from producers. | http://www.fairtrade.org.uk/fortnight | During Fairtrade Fortnight: Promote 10 principles of Fairtade (http://www.wfto.com/fair-trade/10-principles-fair-trade). Food and Fairtrade textiles sold through the school Resources available to order from the website.
|  | 27 | Procurement of chemicals | All can be included | Go Green Week | See above | See above | See above
|  | 28 | Procurement of food | 26,28,29,30,31 | Pass it on Week | See above | See above | See above
|  | 29 | Procurement of general consumables (including furniture and stationary) | 28 | Slow Food Week | See above | See above | See above
|  | 30 | Procurement of services (e.g. maintenance) | 28 | Organic September | Organic September - This year the Soil Association needs you to join their "Small Changes, Big Difference" campaign. And again this year we have a whole month to celebrate all things organic as National Organic Fortnight has been replaced and has now become Organic September. | http://www.soilassociation.org/organicseptember | Guide available on the website
|  | 31 | Transport of goods and services (including construction materials)
Construction | Construction, Refurbishment & Demolition | 32 | Construction on green areas | All can be included | European Week for Waste Reduction | See above | See above | See above
|  | 33 | Use of construction materials | All can be included | Go Green Week | See above | See above | See above
|  | 34 | Use of energy and utilities | All can be included | World Environment Day | See above | See above | See above
|  | 35 | Use and storage of chemicals
|  | 36 | Leaks/spills of cleaning/maintenance materials/chemicals/waste
|  | 37 | Generation of inert/municipal waste
|  | 38 | Generation of hazardous waste (including asbestos)
|  | 39 | Waste recycling (including composting)
|  | 40 | Noise and vibrations
Contractors | Management of contractors | 41 | Management of contractors
Noise and Nuisance | Creation of noise and nuisance | 42 | Noise
|  | 43 | Nuisance
Other events
[5 empty] | Name | Description | Links | Tips and suggestions
|  |  |  | Health | Addressing Anxiety - Disrupting Negative Thoughts. | ENU Health Promotions 2015
[5 empty] | Allergy Awareness Week | ENU Health Promotions 2015
[5 empty] | Bowel Cancer Awareness Month | ENU Health Promotions 2015
[5 empty] | Breast Cancer Awareness Month | ENU Health Promotions 2015
[5 empty] | Diabetes Week | ENU Health Promotions 2015
[5 empty] | Disruptive Innovation Festival | Online three week long event that brings together entrepreneurs, designers, industry, makers, learners and doers to explore and respond to the changing economy. | https://www.thinkdif.co/
[5 empty] | Health Promotion Day | ENU Health Promotions 2015
[5 empty] | Holocaust Memorial day | Celebrated on different days throughout the world
[5 empty] | Information Overload - How to disconnect. | ENU Health Promotions 2015
[5 empty] | Know the 10 Early Signs of Dementia | ENU Health Promotions 2015
[5 empty] | Men's Health Week | ENU Health Promotions 2015
[5 empty] | Mental Health Awareness Week | ENU Health Promotions 2015
[5 empty] | Migraine Awareness Week | ENU Health Promotions 2015
[5 empty] | National Stress Awareness Day | ENU Health Promotions 2015
[5 empty] | Pregnancy and Infant Loss Remembrance Day | Day of remembrance for pregnancy loss and infant death, which includes but is not limited to miscarriage, stillbirth, SIDS, or the death of a newborn. It is observed annually in the United States and Canada and, in recent years, in the United Kingdom and in the Australian States of Western Australia and New South Wales, in Italy on behalf of a charity named Piccoli Angeli
[5 empty] | Strategies for Multigenerational caregiving | ENU Health Promotions 2015
[5 empty] | Stick with it | ENU Health Promotions 2015
[5 empty] | World AIDS Day | Designated 1 December every year since 1988
[5 empty] | World Cancer Day | Founded by the Union for International Cancer Control (UICC) to support the goals of the World Cancer Declaration, written in 2008
[5 empty] | World Health Day | In 1948, the WHO held the First World Health Assembly
[5 empty] | Work Wise Week | Raising awareness about smarter working (flexible working, home working, remote working) amongst employees and employers. Work Wise Week also incorporates National Work from Home Day on Friday 5th June. | www.workwiseuk.org/workwiseweek/
[5 empty] | World Mental Health Day | ENU Health Promotions 2015
|  |  |  | Religious | All Saints' Day | A Roman Catholic and Anglican holiday celebrating all saints, known and unknown.
[5 empty] | Ash Wednesday | The seventh Wednesday before Easter and the first day of Lent, which lasts 40 days. Having its origin sometime before A.D. 1000, it is a day of public penance and is marked in the Roman Catholic Church by the burning of the palms blessed on the previous year's Palm Sunday. With the ashes from the palms the priest then marks a cross with his thumb upon the forehead of each worshipper. The Anglican Church and a few Protestant groups in the United States also observe the day, but generally without the use of ashes.
[5 empty] | Boxing Day | Boxing Day is a holiday traditionally celebrated the day following Christmas Day, when servants and tradesmen would receive gifts, known as a "Christmas box", from their bosses or employers
[5 empty] | Chinese New Year | The most important celebration in the Chinese calendar. Chinese months are reckoned by the lunar calendar, with each month beginning on the darkest day. New Year festivities traditionally start on the first day of the month and continue until the fifteenth, when the moon is brightest. In China, the New Year is a time for family reunions. In the United States, however, many early Chinese immigrants arrived without their families, and found a sense of community by celebrating the holiday through neighbourhood associations
[5 empty] | Christmas | The most widely celebrated holiday of the Christian year, Christmas is observed as the anniversary of the birth of Jesus. Christmas customs are centuries old. The mistletoe, for example, comes from the Druids, who, in hanging the mistletoe, hoped for peace and good fortune. Comparatively recent is the Christmas tree, first set up in Germany in the 17th century. Colonial Manhattan Islanders introduced the name Santa Claus, a corruption of the Dutch name St. Nicholas, who lived in fourth-century Asia Minor
[5 empty] | Diwali | Festival of Lights for Hindu, Sikh and Jain communities
[5 empty] | Easter Sunday | Observed in all Western Christian churches, Easter commemorates the Resurrection of Jesus. It is celebrated on the first Sunday after the full moon that occurs on or next after the vernal equinox (fixed at March 21) and is therefore celebrated between March 22 and April 25 inclusive. This date was fixed by the Council of Nicaea in A.D. 325.
[5 empty] | Eid al-Adha | The Feast of Sacrifice, commemorates Abraham's willingness to obey God by sacrificing his son. Lasting for three days, it concludes the annual Hajj, or pilgrimage to Mecca. Muslims worldwide sacrifice a lamb or other animal and distribute the meat to relatives or the needy.
[5 empty] | Eid al-Fitr | End of Ramadan
[5 empty] | First Day of Ramadan | Beginning of a month-long fast that all Muslims must keep during the daylight hours. It commemorates the first revelation of the Qur'an. Following the last day of Ramadan, Eid al-Fitr is celebrated on Tues. August 8.
[5 empty] | First Sunday of Advent | Advent is the season in which the faithful must prepare themselves for the coming, or advent, of the Savior on Christmas. The four Sundays before Christmas are marked by special church services.
[5 empty] | Good Friday | The Friday before Easter, it commemorates the Crucifixion, which is retold during services from the Gospel according to St. John. A feature in Roman Catholic churches is the Liturgy of the Passion; there is no Consecration, the Host having been consecrated the previous day. The eating of hot-cross buns on this day is said to have started in England.
[5 empty] | Halloween | Dedicated to remembering the dead, including saints (hallows), martyrs, and all the faithful departed believers
[5 empty] | Hanukkah | Jewish Festival of Lights, This festival was instituted by Judas Maccabaeus in 165 B.C. to celebrate the purification of the Temple of Jerusalem, which had been desecrated three years earlier by Antiochus Epiphanes, who set up a pagan altar and offered sacrifices to Zeus Olympius. In Jewish homes, a lamp or candle is lighted on each night of the eight-day festival.
[5 empty] | Holi Day | Spring festival, also known as the festival of colours or the festival of love. It is an ancient Hindu religious festival which has become popular with non-Hindus in many parts of South Asia, as well as people of other communities outside Asia.
[5 empty] | Mawlid al-Nabi | Celebrates the birthday of Muhammad, the founder of Islam. It is fixed as the 12th day of the month of Rabi I in the Islamic calendar.
[5 empty] | Muharram | The month of Muharram marks the beginning of the Islamic liturgical year. On the tenth day of the month, many Muslims may observe a day of fasting, known as Ashurah.
[5 empty] | Palm Sunday | The Sunday before Easter to commemorate the entry of Jesus into Jerusalem.
[5 empty] | Passover | The Feast of the Passover, also called the Feast of Unleavened Bread, commemorates the escape of the Jews from Egypt. As the Jews fled, they ate unleavened bread, and from that time the Jews have allowed no leavening in their houses during Passover, bread being replaced by matzoh.
[5 empty] | Pentecost (Whitsunday) | Commemorates the descent of the Holy Ghost upon the apostles 50 days after the Resurrection. Whitsunday is believed to have come from "white Sunday," when, among the English, white robes were worn by those baptized on the day.
[5 empty] | Rosh Hashanah (Jewish New Year) | Marks the beginning of the Jewish year 5768 and opens the Ten Days of Penitence, which close with Yom Kippur.
[5 empty] | Shavuot (Hebrew Pentecost) | Sometimes called the Feast of Weeks, or of Harvest, or of the First Fruits, falls 50 days after Passover and originally celebrated the end of the seven-week grain-harvesting season. In later tradition, it also celebrated the giving of the Law to Moses on Mount Sinai.
[5 empty] | Shrove (Mardi Gras) | Tuesday before Ash Wednesday and marks the end of the carnival season, which once began on Epiphany but is now usually celebrated the last three days before Lent. In France, the day is known as Mardi Gras (Fat Tuesday), and celebrations are held in several American cities, particularly New Orleans. The day is sometimes called Pancake Tuesday by the English because fats, which were prohibited during Lent, had to be used up.
[5 empty] | St Andrew’s Day | Scotland
[5 empty] | St David’s Day | Wales
[5 empty] | St George’s Day | England
[5 empty] | St Patrick’s Day | Ireland
[5 empty] | Yom Kippur (Day of Atonement), | The end of the Ten Days of Penitence that began with Rosh Hashanah. It is described in Leviticus as a Sabbath of rest, and synagogue services begin the preceding sundown, resume the following morning, and continue to sundown.
|  |  |  | Other | April Fools’ Day | The origins of April Fool's Day are uncertain. Some see it as a celebration related to the turn of the seasons, while others believe it stems from the adoption of a new calendar
[5 empty] | Beltane | Celtic festival of fire (mark the start of the summer)
[5 empty] | Bonfire night | There are many food items that are associated with Bonfire Night. Toffee apples, treacle toffee, black peas, and parkin are traditionally eaten around Bonfire Night in parts of England
[5 empty] | Burns’ Night | Scotland
[5 empty] | Communication Skills for Collaboration | ENU Health Promotions 2015
[5 empty] | Coping with Change | ENU Health Promotions 2015
[5 empty] | Creating a Personal Development Plan | ENU Health Promotions 2015
[5 empty] | Flag Day | Commemorates the adoption by the Continental Congress on June 14, 1777, of the Stars and Stripes as the U.S. flag. Although it is a legal holiday only in Pennsylvania, President Truman, on Aug. 3, 1949, signed a bill requesting the president to call for its observance each year by proclamation.
[5 empty] | Fresher's Week and Re-fresher's week | The NSA organises a Freshers' Week and a Re-Fresher's week during the first week before term 1 and 2 begin. The event is full of entertainment and events and it is a good time for the Sustainability team to engage with the rest of the university. | http://napierstudents.com/
[5 empty] | International Day for the Elimination of Racial Discrimination | The International Day for the Elimination of Racial Discrimination is observed annually on 21 March. On that day, in 1960, police opened fire and killed 69 people at a peaceful demonstration in Sharpeville, South Africa, against the apartheid pass laws. Proclaiming the day in 1966, the United Nations General Assembly called on the international community to redouble its efforts to eliminate all forms of racial discrimination.
[5 empty] | International Day of Happiness | Established by the United Nations General Assembly on 28 June 2012.
[5 empty] | International Mother Language Day | First announced by UNESCO in 1999
[5 empty] | International Women's Day | The earliest Women’s Day observance was held on February 28, 1909, in New York; it was organized by the Socialist Party of America in remembrance of the 1908 strike of the International Ladies' Garment Workers' Union. There was no specific strike happening on March 8, despite later claims.
[5 empty] | Martin Luther King Day | A US holiday observed on the third Monday in January that honours the late civil rights leader.
[5 empty] | May (Labour) day | An annual holiday to celebrate the achievements of workers. Labour Day has its origins in the labour union movement, specifically the eight-hour day movement, which advocated eight hours for work, eight hours for recreation, and eight hours for rest. For many countries, Labour Day is synonymous with, or linked with, International Workers' Day, which occurs on 1 May.
[5 empty] | Remembrance Day | Also known as Poppy Day is a memorial day observed in Commonwealth of Nations member states since the end of the First World War to remember the members of their armed forces who have died in the line of duty. The day, specifically designated by King George V on 7 November 1919.
[5 empty] | Summer solstice | The summer solstice occurs when the tilt of a planet's semi-axis, in either the northern or the southern hemisphere, is most inclined toward the star (sun) that it orbits. Earth's maximum axial tilt toward the sun is 23° 26'. This happens twice each year, at which times the sun reaches its highest position in the sky as seen from the north or the south pole.
[5 empty] | The Queen’s Official Birthday | Since 1748 to celebrate the king or queen’s birthday in June
[5 empty] | Valentine’s Day | The holiday's roots are in an ancient Roman fertility festival. Circa 496, Pope Gelasius I recast this pagan festival as a Christian feast day in honour of St. Valentine, but there are at least three different early saints by that name. How the day became associated with romance remains obscure, and is further clouded by various fanciful legends
[5 empty] | World Day of Social Justice | General Assembly of the United Nations from starting in 2009
[5 empty] | Zero Discrimination Day | Linked to discrimination around AIDS
Information from this section has been obtained from online sources and Edinburgh Napier University Academic Developers.

## 2.d Hints and tips
Hints and Tips for planning promotion
2017-07-20
USEFUL TOOLS
Design
Name | Description | Link or location | Tips
CANVA | Easy to use free online design program. Excellent for creating posters, bicycle tags, TV screen images and so forth. | https://www.canva.com/ | When using a full page photo, download the highest resolution to avoid pixelation.
Pixlr | Free online photo editor | https://pixlr.com/desktop
Photoshop | Image editor | Edinburgh Napier University Application window. Click on: Faculty of Engineering, Computing and Creative Industries. Click on: School of computing. The application should be located in the top row.
Paint | Image editor
Gimpshop | Image editor, free alternative to photoshop | http://www.gimpshop.com/ | Very slow program and difficult to understand. But may be useful for someone who has Photoshop experience.
Autodesk DWG TrueView 2016 | Free download available. Helps you create and edit building drawings and plans. | To get a PDF from this program click on the following: - Plot (icon of printer) -Select: Cute PDF printer, paper size (of your choosing) - For 'What to plot' click: extents. - Plot styles table: click: monochrome (if you want black and white) - Then shade plot 'Legacy wireframe' (for picture clarity) - Then untick 'plot object lineweights'
Help and Advice Forums
Name | Description | Link or location
JISC Mail | A JISCMail list is essentially a mailing list. Each JISCMail list holds the email addresses of anyone that has signed up to it. If you send an email addressed to a JISCMail e.g. IHAVEAQUESTION@JISCMAIL.AC.UK that email will go to everyone signed up to that list. You will not however, be able to see the individual email addresses of others signed up to that list, nor will anyone else be able to see your individual email address. They will only see the JISCMail address. This means you can engage with the community on that list, without sharing your email with the unknown. The JISCMail posts are also carefully monitored by the EAUC to ensure appropriate content and use by all members. There are many distribution lists available such as: EAUC UK All members, EAUC Scotland UCCCfS, Community Engagement TSN, Energy TSN, Education for Sustainable Development (FE) TSN, Sustainable Construction TSN, Sustainable ICT TSN, Sustainable Procurement TSN, Travel & Transport TSN, Waste TSN | To register: info@eauc.org.uk
TIPS
Name | Description | Link or location
Fairtrade producer visit | Two Fairtrade producers from Mauritius came to visit the University on March 3rd 2015. The producers spent most of their time in the reception area but they were also scheduled to talk in a classroom for 15 minutes. Unfortunately there was no audience for the talk. In the future it would be useful to consider arranging the producers to speak in a relevant class (such as at the start of a lecture), rather than have an audience meet in a certain room.
Date and timing of events | It is best to alternate dates and timings of similar events because staff and student members don't all work on the same days. For example: it would be best to hold quarterly Swishes during different days of the week and different times to ensure the greatest number of people can attend at least one event.
Messages from external organisations | Messages from external organisations can be altered to suit University digital signage screens and branding. Wording, layout ect can be changed.
Promotion within the Unversity | Promotion done within the University needs to be monitored for errors. It is useful to encourage other University departments (such as ERC) to re-communicate certain information before a major event, activity ect, whenever it is appropriate. It is up to the Environmental Sustainability Team to remember these points. Also, the University requires that all promotion follow certain brand guidelines. These can be found on the staff intranet, page 42 of the document "Edinburgh Napier University's Brand Guidelines" | http://staff.napier.ac.uk/services/corporateaffairs/exchange/Documents/edinburgh-napier-brand-guidelines.pdf | Or, follow these links: Edinburgh Napier Staff Intranet > Service Depts > Marketing, Brand and Communications > Marketing Exchange > Brand Guidelines
USEFUL WEBSITES
Name | Description | Link or location |  | Example 1 | Example 2
Hootsuite | HootSuite allows for managing social media accounts, using this tool, you can schedule Twitter and Facebook posts ahead of time. As well, it provides analytics for all the social media accounts linked to the website. | https://hootsuite.com/ | Issues: Scheduled posts with images need to be opened by Twitter followers in order to be seen (Circled in Example 1). Also, a mysterious link appears in the post (underlinedExample 1). Although this website is useful, it is better to post anything with images separately in order for the image to be seen immediately, this may influence the number of 're-tweets' and 'favourites' it receives (Example 2).
Mailchip | Mailchimp is a great website for designing newsletters. It is free and easy to use. Try to keep the tone chatty and conversational. Use other newsletter's as examples. | http://mailchimp.com/
General tips:
Ensure the University is labelled as "Edinburgh Napier University" not "Napier University"
Asset bank stores good quality images created by the University photographer
Keys for poster cabinets in the Sighthill lecture hallways can be found with the Faculty Operations Manager in 2.B.23
The internal mail service can be used to send posters to Campus managers based at the other two campuses
It is useful to make posters regarding static information relating to the team (eCycle hire ect) for digital sigange screens.

## Tasks (hidden)
Individual tasks March 2015
[7 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
|  | PLAN | PLAN | ACTUAL | EVENT | PERCENT
| ACTIVITY | START | DURATION | START | DURATION | COMPLETE | PERIODS
 | time axis 2014-09-01 to 2015-08-31
Sept | Trimester 1 | 2014-09-08 | 103 | 2014-12-20 | bar: 2014-09-08 to 2014-12-20; 2015-04-01; 2015-05-01; 2015-06-01
Sept | Freshers Fair and Inductions | 2014-09-02 | 4 | 2014-09-06 | 5 | 100% | bar: 2015-04-01; 2015-05-01; 2015-06-01
Oct | Liftshare week | 0 | 0 | 0 | 0 | 100% | bar: 2015-04-01; 2015-05-01; 2015-06-01
Oct | Energy Saving week | 2014-10-06 | 14 | 2014-10-20 | 5 | 100% | bar: 2015-04-01; 2015-05-01; 2015-06-01
Nov | European Week for Waste Reduction | 2014-11-10 | 12 | 2014-11-22 | 7 | 100% | bar: 2015-04-01; 2015-05-01; 2015-06-01
Dec | Assessment week | 0 | 0 | 2014-12-08 | 12 | 100% | bar: 2015-04-01; 2015-05-01; 2015-06-01
Dec | Christmas switch off | 2014-12-06 | 14 | 2014-12-20 | 14 | 100% | bar: 2015-04-01; 2015-05-01; 2015-06-01
Dec | Christmas holidays | 0 | 0 | 2014-12-22 | 14 | 100% | bar: 2015-04-01; 2015-05-01; 2015-06-01
Jan | Inter Trimester Week | 0 | 0 | 2015-01-05 | 6 | 100% | bar: 2015-04-01; 2015-05-01; 2015-06-01
Jan | Trimester 2 | 2015-01-12 | 117 | 2015-05-09 | 0
Jan | NSS Survey time | 0 | 0 | 2015-01-13 | 80 | 40%
Jan | MyNapier Page Update | 2015-01-14 | 57 | 2015-03-12 | 0 | 0% | bar: 2015-03-01 to 2015-03-12
Jan-Sept | Communication strategy | 2015-01-07 | 62 | 2015-03-10
Feb | Go Green Week | 2015-01-27 | 14 | 2015-02-09 | 7 | 0%
Feb/March | Essential Cycle Skills and Bike Maintenance | 2015-01-27 | 29 | 2015-02-25 | 1 | 0%
March | Essential Cycle Skills | 2015-01-27 | 36 | 2015-03-04 | 1 | 0%
March | Fairtrade Fortnight | 2015-01-27 | 36 | 2015-02-23 | 14 | 0%
March | Pass it on week | 2015-02-18 | 17 | 2015-03-07 | 8
March | Earth Hour | 2015-03-16 | 12 | 2015-03-28 | 1 | 0%
April | Easter Break | 0 | 0 | 2015-04-03 | 14 | 0%
April | John Muir Day | 2015-04-01 | 17 | 2015-04-18 | 8
April | Assessment week | 0 | 0 | 2015-04-27 | 12 | 0%
May | Trimester 3 | 2015-05-18 | 103 | 2015-08-29
May | Student move-out dates for accommodation | 2015-05-27 | 2 | 2015-05-29
For me | MyNapier Page Update | 2015-03-30 |  | 2015-03-30 | 100
May | BHF donation collection | 2015-04-02 | 60 | 2015-06-01
May | Walk to work week | 2015-05-04 | 7 | 2015-05-11 | 5 | 0%
May | Inter Trimester Week | 0 | 0 | 2015-05-10 | 7 | 0%
May | Basic Bicycle Maintenance | 2015-05-07 | 21 | 2015-05-28 | 1
June | Slowfood week | 2015-05-25 | 7 | 2015-06-01 | 7 | 0%
June | EU Sustainable energy week | 2015-06-08 | 7 | 2015-06-15 | 5 | 0%
July | Third SWISH | 2015-07-09 | 14 | 2015-07-23 | 1
Aug | Assessment week | 0 | 0 | 2015-08-17 | 12 | 0%

## 3.a Evidence
Promotion Communication Evidence
2017-07-20 |  |  |  | Name and Date
Channel | Ref # | Name | Specific locations | Christmas Switch Off December 2014 | Basic Bike Maintenance 25/02/2015 | Essential Cycle Skills Workshops 25/02/2015 and 03/03/2015 | Fair Trade Producer Visit Event 04/03/2015 | ResLife Swish (11/03/15) | Staff Swish (13/03/15) | Fairtrade Clothing sale (EPONA) (02/03/15, 04/03/15 and 05/03/15) | Earth Hour 2015 28/03/2015 | Sighthill Park Spring Cleaning 27/03/2015 | Walk to Work Week May 11-15 2015 | Active Transportation Training Sustrans 21/05/2015 | Basic Bicycle Maintenance Workshop 28/05/2015 | Guided Bicycle ride 10/06/2015 | EPP event | Essential Cycling Skills 25/06/2015 | Recycle Week through Zero Waste Scotland 22-26 June 2015 | eCycle promotion. Ongoing | Active Travel Champion Training 12.08.2015 | Campus tour guided cycle ride (Oct 6 2015)
Electronic Options
Twitter | 1.a | Sustainable Edinburgh Napier University | [11 empty] | Cover page and Tweets | Cover page and Tweets |  |  | Cover page and Tweets |  | Profile picture | Cover page and Tweets | 1x
| 1.b | Edinburgh Napier University | [18 empty] | 5x | 1x
| 1.c | NSA |  |  |  | 2x | 4x |  |  |  | 2x | 2x |  |  |  | 2x |  | 3x |  | Healthy living fair | 1x | 1x
| 1.d | Edinburgh Napier Library | [18 empty] | 1x
| 1.e | Edin Napier IT Bytes
| 1.f | Napier Vbase
| 1.g | [EN] Gage Fitness | [18 empty] | 2x | 1x
| 1.h | Supported Ed Napier
| 1.i | Napier Fresher's '15 | [18 empty] | 1x
| 1.j | Team Napier | [18 empty] | 1x | 1x
Facebook | 2.a | Edinburgh Napier University Environmental Sustainability |  | This page did not exist at the time when this information was promoted. | [10 empty] | Banner and Posts |  |  | Banner and Posts |  | Profile picture | Banner and Posts | Post
| 2.b | Edinburgh Napier University Student Accomodation | [18 empty] | 1x | Post
| 2.c | Edinburgh Napier University | [18 empty] | 1x | Post
| 2.d | Edinburgh Napier University Students' Association
| 2.e | [EN] Gage Fitness
| 2.f | Team Napier
| 2.g | Edinburgh Napier International
| 2.h | Edinburgh Napier University careers
| 2.i | Enjoy (catering)
Pinterest | 3.a | Edinburgh Napier University Environmental Sustainability Team
| 3.b | ResLife Pinterest
Website | 4.a | Environmental Sustainability Team (Staff Intranet page)
| 4.b | Edinburgh Napier University Internet Page
| 4.c | Edinburgh Napier University Staff Intranet Page
| 4.d | Edinburgh Napier University MyNapier Page | [18 empty] | News, banner image and student newsletter | News, and student newsletter
E-mail | 5.a | Environmental Sustainability Team main e-mail address
| 5.b | Student HTML e-mail
| 5.c | Staff HTML e-mail
DIGITAL | 6.a | P&F Communicate E-newsletter
| 6.b | eCycle newsletter
| 6.c | Digital Signage (TV and computer screen sizes)
| 6.d | Moodle
| 6.e | YouTube
| 6.f | Instagram
| 6.g | Videos
| 6.h | Text Messaging
Physical Options- On-Site Promotions
Paper promotions | 7.a | A4 promotional posters | Sighthill 7.B. 08 (print room)
Sighthill 7.B. 36 (kitchen)
Sighthill 6.B.17 (kitchen)
Sighthill 6.B.21 (kitchen)
Sighthill 6.B 08 (print room)
Sighthill 5.B.08 (print room)
Sighthill 5.B.17 (kitchen)
Sighthill 5.B. 21 (kitchen)
Sighthill 4.B.08 (print room)
Sighthill 4.B. 26 (kitchen)
Sighthill 4.B. 47a (kitchen)
Sighthill 3.B. 08 (print room)
Sighthill 3.B. 26 (kitchen)
Sighthill 3.B. 47a (kitchen)
Sighthill 2.B. 08 (print room)
Sighthill 2.B.34 (print room)
Sighthill 1.B. 02 security
Sighthill 1.B.14 (print room)
Sighthill 1.B.16 (kitchen)
Sighthill 1. B. 27 Student hub poster board
Sighthill Level 1 D outside Lecture Theatres
Sighthill Level 2 D classroom hallway
Sighthill Level 3 D classroom hallways
| 7.b | A4 promotional posters | Craiglockhart TBD
Craiglockhart TBD
Craiglockhart TBD
Craiglockhart TBD
| 7.c | A4 promotional posters | Merchiston Kirby computing center
Merchiston Four A0 posters in main walking area (Fair Trade event posters only)
Merchiston Poster board by Apex café
Merchiston Poster board by reception area
Merchiston Poster board in music hallway
| 7.d | A0 poster boards
| 7.e | Message board in lift
| 7.f | Poster holders in toilets
| 7.g | Table talkers
| 7.h | Invitations (to events)
| 7.i | Flyers or leaflets
| 7.j | Pamphlets
| 7.k | Bike tags
| 7.l | Poster holders in toilets
| 7.m | Table talkers
| 7.n | Invitations (to events)
| 7.o | Flyers
| 7.p | Pamphlets
| 7.q | Laminated posters
During event promotion | 8.a | Re-useable pop up display board
| 8.b | Stalls/ Booths
Other Options
Personal promotions | 9.a | Inductions (staff and student)
| 9.b | Ambassadors
| 9.c | Class shout outs
| 9.d | Volunteers
| 9.e | Class reps
| 9.f | Training session
| 9.g | Design Competition
| 9.h | Interviews
| 9.i | Focus groups
| 9.j | Questionnaires
| 9.k | Meetups
| 9.l | Campus users groups
| 9.m | Awareness Events
| 9.n | Exhibitions
| 9.o | Road shows
| 9.p | Class visits
| 9.q | Start a campaign
| 9.r | Enlist the help of bloggers
Other Options | 10.a | Prizes
| 10.b | Maps
| 10.c | Stickers (ex- floor)
| 10.d | T-shirts
| 10.e | Photocall
| 10.f | Speakerphone shout-outs
| 10.g | Photography challenge
| 10.h | Yik Yak (anonymous social media app)
| 10.i | Radio
| 10.j | Feedback forms
| 10.k | Coordinated dancing
| 10.q | Movement sessions, simple 5 minutes (‘wiggle it, waggle it, twerk it, work it – just DON’T sit on it’)
| 10.r | Run around to win a free coffee/tea/ Fairtrade chocolate

## 3.b Lessons and future ideas
Lessons and future ideas for promotion and events that occurred Academic year 2014/2015
2017-07-20
Lessons and Notes | Ideas for the future | Things that worked | # of attendees | # people reached (stats from Facebook)
Essential Cycle Skills
Two of these events were held in February/March 2015. One of them was successful in recruiting participants and one was not. It is possible that more than two weeks was needed to spread the message regarding the events to staff and students. The second workshop was successful. Don't hold workshops at times when you (the provider) are not free. | Hold the events during times when it is convenient for staff and students. | Sending a e-mail to all staff members with a parking pass may have led to the increase in numbers for the workshops. | Workshop 1= 0 Workshop 2= 4
Basic Bicycle Repair/ Maintenance
This workshop was a success. There was a backlog of individuals interested in the course. Another one will be held at the end of May 2015. | Hold the event during a time and on a date when it is convenient for staff and students. | The idea of the course is great. The location (classroom at Sighthill) worked. | 7
Fairtrade Fortnight Producer Visit Tuesday March 3rd 2015
The producer arrival was not very successful. In general it is hard to engage students and staff at the University but especially so when they are required to do something. In this case, the requirement was: come to a certain room at two different times. The first timeslot did not work out because it was too close to the start of the session and the producers were held back at their first meeting. The second timeslot had no participants. Some people came to see the stall in the reception but it was clear that few people came especially to see the producers. It is possible that the location was inadequate, or the timing was not good with student schedules. | An idea to improve participation of staff and students at this event is to contact relevant lecturers (who teach this subject or something similar) beforehand and enquire whether the producers can come to the class to speak. Maybe a few month's notice is best. Another idea is to have the session at a different campus, perhaps Merchiston reception area because it is a high traffic area. Instead of having a Fairtrade event (because it seems like people tend to think they know what FT is all about and don't really want to learn more), have a general Food event. Look at other interesting topics too like MSC fish for example. | Having the reception space at Sighthill was good. There was a great deal of pamphlets on the table which attracted interest. The producers brought sugar to sell, this attracted at least one student. A great deal of pamphlets, stickers and other promotional material were obtained for free from the Fairtrade Foundation. These were useful tools to promote the idea of Fairtrade and our event. | A few people (~10) came to the stand
Student Swish with ResLife Wednesday March 11th 2015
This event was not a success at all. No students provided donations and no one appeared for the event despite heavy promotion. It is possible that the location of the event was unsuitable since most students still do not know where Bainfield Bar/Café is located. Also, it is possible that students in general do not have much to swap. | Hold the event in a different location, such as on-campus. Instead of a swish, maybe have repair workshops (contact Transition Heriot-Watt, they will have ideas) Students may be more likely to attend a workshop where they learn something instead of an event where they need to provide items. | The idea of bringing food was good. Also, the free sewing lessons may have brought in some people. | 0
Staff Swish Friday March 13 2015
Left over stock will be used at the next Swish event which could be May 20th at lunch, it is currently being stored under Richard’s old desk and will soon be moved into a cupboard in the print room About half the stock was taken up by participants during the Swish Friday may not be the best day for this kind of event because most people aren’t here or they leave at lunch, it was not busy between 1-2 People sometimes came in just to ask questions and take pamphlets It took two days to prepare, organise and deliver the event. From getting donations to setting up and taking down desks/ hangers. | Hold this event during different days' of the week if next sessions occur. This one happened on a Friday. Have the next Swish on a Wednesday and the following one on a different day. There were queries regarding a future swish, it was recommended that if there are more swishes then people will begin to understand what they mean and will be more involved. The room location was great because it was right beside the toilet The mirror was a good idea. | Approximately 80--90 items were donated which included books, accessories and clothing (both male and female). The idea of bringing donations the day before and the day of the event was good. Providing "stamps" or little cards with the number of donated items by each individual was also a great way to ensure participation during the event and a fair way to swap items. The free organic/ Fairtrade chocolate was popular. The re-use pamphlets were a great hit as well. | Donation providers: 11 Participants: ~20
Walk to Work Week May 11-15
The success of the week was not easy to measure since the website data was not available after the week was complete. | In the future it would be a good idea to hold Walk at Work sessions during the week, perhaps a 30 minute walk for staff and students at each campus? A designated walk leader would need to be identified and made available and promotion should begin ~1 month in advance alongside the Walk to Work week promotion. This is especially needed for those who cannot walk out to campus (due to distance or other responsibilities). This idea was highlighted through informal discussions with employees at the Sighthill campus. |  |  | 27
Active Travel Champion Training (not successful)
This did not go through due to too few registrations. | This will be attempted again, August 20th with the hope that more time to promote the event will help gain interest.
Basic Bicycle Repair/ Maintenance second session
This session was a great success. Two additional people came along to the course who did not previously register, so the course was at over-capacity. Promoting the information through the ResLife Accommodation Facebook page helped raise the number of post views. Grease Monkey bicycle repair pamphlets were provided to the participants who appreciated the extra take-away information. | Advertise more than a month in advance for courses that have a two week cancellation policy. | Holding the session at the hours chosen (4-6:30) was ideal for some (not as much for those with families though). | 7 | 265
Guided Bicycle Ride June 10 2015
Create Risk Assessment and obtain important necessary items (such as a First Aid Kit) at least 1-2 weeks in advance. | Continue holding these sessions, people may become more interested over time. | Providing an eCycle to the participant was a good idea because they were able to enjoy the ride and not be stressed out by the hills or exhausted at the end of the cycle and they did not lag behind at all. The risk assessment was comprehensive and covered most of the issues that were encountered. | 1 (with 2 other people interested in taking part at a different date) | 23
Essential Cycle Skills round 2
Course participants need to be informed (by members of the Environmental Sustainability Team) about the location of the room where the course will take place. | Before allowing someone to loan an eCycle, it would be useful to ask for a basic skills test and if the potential user or the person loaning the bike is still unsure of the person's abilities, it is a good idea to ask them to attend this course before loaning a bike. | Holding the session at Merchiston is best because the course leader is able to provide practical training in the parking lot. | 3 | 28
Active Travel Champion Training round 2 (successful)
It took about two days to plan, create and send out promotion. I tried to make the material unique, different and interesting. Registrations occurred through the Sustainability Engagement Officer who was able to monitor the communication that was sent to the participants. It was clear that previous communication through Sustrans did not include room number. | Ask the participants how they found out about the course. Allow more time to promote information. | Altering the wording on previously used promotional material may have had a positive influence on the people who came to the session. When asked what method worked they said: poster in print room and MyNapier events news banner. | 3
Guided Bicycle Ride Sept 11 2015
The bicycle ride was advertised at the September 5th Welcome fair only because a maximum of 8 people could come on the ride and 8 people signed up. However, of the eight people, one came to the actual event despite a pre-event reminder e-mail. | Ask participants for their telephone numbers so a reminder text can be sent before the event. Also, ask participants (in the pre-ride e-mail) to inform you if they cannot come so that space is made for other potential participants. Putting a timeline on registration may help, so ask for everyone to sign up before 12 o'clock the day before or something. | According to the participant, the route choice (NCR 754 on the way to Sighthill via Craiglockhart, then Route 8 on the way back to town) was great. | 1 | n/a
Guided Bicycle Ride Oct 6 2015
Ideas for more events
· Books and wine swap. Could use Fairtrade wine.
· Easter Fairtrade chocolate event
· Sell chocolate to stressed out students during exam time
· Cycle ride options: travelling into the city, ladies or gents ride out, eCycle introduction ride, staff cycle session, lunchtime cycle escape (20mins)
· Walk to Work week: provide freebies? Set goals like: achieve 10,000 a day, provide maps, information on how long it takes to get to the campuses from town. Create walking groups at each campus potentially?
· Integrate students with the local community by providing information about local businesses. For example: The Health Strategy Group food co-op in Broomhouse http://healthstrategygroup.org.uk/
· Connect with the curriculum by involving lecturers
· Establish a connection with the Community gardens next door at Edinburgh college.
· Walk At Work, 30 minute lunchtime sessions potentially at each of the campuses if there are ambassadors available
· June big Walk day: Get ambassadors from the other campuses to help
· Bring in the Changeworks efficient driving simulation vehicle for people to try out
· Photography challenge
- You can add stuff we’ve already held like: Basic Bicycle repair courses, Dr.Bike sessions, Essential Cycling Skills workshops, SWISH events ect
- Also, in addition to Fairtrade you can also have an organic cookoff
- perhaps even a session with a professional chef, I’ve heard of a place that let people come up with cool workable recipes which had the potential of being added to the canteen menu… don’t know how hard it would be to implement that here, but worth a try.
- Cooking/nutrition workshops are an idea
- trashion show
- recycling game/challenge
- scavenger hunt (lots of different options with this)
- sewing lessons
- upcycling fashion show
- hold some remade in Edinburgh classes http://www.remadeinedinburgh.org.uk/workshops-autumnwinter-2015/
- Slowfood week wine tasting session (the Co-op once donated some Fairtade wine for a similar occasion, you can ask Jamie for more info)
- blogging/vlogging competition- blog/vlog about something relating to sustainability at the Uni to win a prize
- selfie run
- blackout event (during Earth Hour a few years back students went around and photographed iconic Napier and Edinburgh buildings to see how they’re doing then they put them up on social media)…
Fall colours cycle or walk
Ideas for cycle rides:
· RSPB nature ride
· History and Heritage ride
· Halloween themed ride (maybe a tour of graveyards and make it spooky)
· Fairtrade food and drink ride
· Medical Ride
· Sports tour – visiting the large sporty type things but also obscure ones like the curling stadium.
· Architectural tour, checking out Edinburgh's historical buildings
· On another note: Re-jiggle the name of events, instead of Fairtrade for example call it: Social procurement for example.

## 3.d Useful resources and links
Useful resources and links for promotion
2017-07-20
Topic | Type of resource | Name | Link | Description
Jobs/Volunteer opps | Link to organisation | Earthwatch | http://eu.earthwatch.org/ | Earthwatch is an international environmental nonprofit organization that funds field expeditions in more than 50 countries
| Link to organisation | Environmentjob.co.uk | http://www.environmentjob.co.uk/jobs | Welcome to environmentjob. With hundreds of advertisers and 59,000 subscribers, we’re by far the UK’s busiest environmental job site. Happy job hunting!)
| Link to organisation | Bright Green Business | http://www.brightgreenbusiness.org.uk/ | Bright Green Business, provides student and graduate placements
Food | Link to organisation | Edinburgh Local Food network | http://www.edinburghfood.org/ | The ‘Edinburgh Local Food Network’ (ELFN) is an informal group of organisations and individuals who care about the availability of local food in the Edinburgh area. We support the development of a truly sustainable food system for our region
| Link to organisation | Edinburgh Farmers’ Market | http://www.edinburghfarmersmarket.co.uk/ | Edinburgh Farmer’s Market
Community | Link to organisation | Out of the Blue arts and education trust | http://www.outoftheblue.org.uk/ | Former military building into a participatory and inclusive arts and cultural centre, with artists’ studios, rehearsal and performance arenas, exhibition spaces and a well-reviewed café. The Out of the Blue Drill Hall is a vibrant, fun, and inclusive place, where people can experience all kinds of innovative contemporary arts, enjoy the creative atmosphere, meet, discuss, eat, relax, learn
General sustainability | APP | Joulebug | http://joulebug.com/ | JouleBug is the easy way to make your everyday habits more sustainable, at home, work, and play. Discover how you and your friends can use resources—without using them up, with this newly designed app. Buzz whenever you do something sustainable. Earn pins, badges and points for discovering new ways to go green.
| Website for organisation | New Caledonian Woodlands | http://newcaledonianwoodlands.org/ncw-events/ | New Caledonian Woodlands is a charity with two primary aims rooted at our core: to encourage environmental sustainability and to support people to improve their mental well-being. They do with re-skilling workshops and outdoor trips to help nature (for example tree pruning, re-forestation ect) "We deliver ‘planet projects’ focused on encouraging people to migrate towards greener lifestyles and ‘people projects’ focused on supporting adults experiencing mental ill-health and social isolation towards improved well-being, more active lives and employment. Whether planting new woodland or managing old ones, making furniture from trees felled by hand, pressing hand-picked apples for juice or learning more about our environmental impact and how to reduce it, New Caledonian Woodlands is busy in the woods most days – working with over 1,000 people per year."
| Website for group | Transition Edinburgh | https://transitionedinburgh.wordpress.com/ | Transition Edinburgh connects and supports community groups, and initiates practical projects that strive for a greener, fairer, healthier and more resilient Edinburgh. They hold lots of events and share interesting information about activities/events happening in Edinburgh that are sustainability related.
| Link to organisation | Himalayan Centre for arts and culture | http://www.himalayancentre.org/ | Our goal is to create a vibrant centre in the heart of Leith, open to everyone, offering a theatre, a cafe and space for activities including dance, drama yoga and art exhibitions. It will be something unique to the capital and wil breathe new life into a much-loved listed building.
| Link to organisation | Scottish Environment Protection Agency | http://www.sepa.org.uk/ | Our role in protecting the environment and human health is wide-ranging, including environmental regulation, mitigating and adapting to climate change, monitoring and reporting on the state of our environment, raising awareness of environmental issues, engaging with the public through citizen science projects, and resolving environmental harms.
| Link to organisation | Keep Scotland Beautiful | http://www.keepscotlandbeautiful.org/ | Keep Scotland Beautiful is the charity that campaigns, acts and educates on a range of local, national and global environmental issues to change behaviour and improve the quality of people’s lives and the places they care for. We are committed to making Scotland clean, green and more sustainable
| Link to organisation | EAUC main website | http://www.eauc.org.uk/home | Environmental Association for Universities and Colleges. The EAUC is the environmental and sustainability champion within Further and Higher Education in the UK. We are a Member association supporting Universities and Colleges across the UK
| Link to organisation | Friends of the Earth Scotland | http://www.foe-scotland.org.uk/ | We are a campaigning organisation that appeals to all walks of life and brings society together with a shared vision of a better place to live
Waste | Link to organisation | Love Food Hate Waste organisation | http://www.lovefoodhatewaste.com/ | Not for profit organisation that provides practical advice on reducing food waste
| APP | Love Food Hate Waste APP | http://www.lovefoodhatewaste.com/ | “easily keep track of food planning, shopping, cooking meals and making the most of leftovers. The App also has lots of great recipe ideas and tips for using forgotten foods and leftovers to make great tasting meals.” · Loads of great recipes with simple step-by-step instructions, with new recipes added all the time · Discover recipes instantly that you can make with ingredients you already have in your kitchen · Portion Planner: we can help you calculate how much you need of the most popular foods · Meal Planner: a diary for planning recipes, meals and leftovers up to 14 days in advance · My Kitchen: store all the info about what you've got at home in your fridge, cupboard and freezer · Shopping List: track everything you need for your planned meals and alerts you if you have duplicates of any ingredients · Achievements: unlock badges and share your culinary accomplishments with friends & family
| Link to organisation | The City of Edinburgh Council waste pages | http://www.edinburgh.gov.uk/waste | Edinburgh Council bins and recycling information page
| Link to organisation | Recycle for Scotland | http://www.recycleforscotland.com | Links to recycling information in Scotland and information regarding the annual Recycle Week event
| Link to organisation | The Edinburgh Tool Library (ETL) | http://edinburghtoollibrary.org.uk/ | The Edinburgh Tool Library (ETL) is based on a North American model. It allows communities to have access to tools at low cost…)
| Link to organisation | Remade in Edinburgh | http://www.remadeinedinburgh.org.uk/ | Remade in Edinburgh is a social enterprise which teaches repair skills and works in partnership to campaign for goods to be built to last.)
| Link to organisation | Zero Waste Scotland | http://www.zerowastescotland.org.uk/ | Zero Waste Scotland is helping Scotland to become more efficient in its use of resources
| Link to organisation | Changeworks | http://www.changeworks.org.uk/ | We are one of Scotland’s largest environmental charities – a thriving social enterprise with over 20 years’ experience in sustainability. We work with organisations, communities and individuals to deliver practical solutions that reduce carbon emissions, fuel poverty and waste
| Link to organisation | The Freecycle Network | https://groups.freecycle.org/ | The Freecycle Network™ is made up of 5,258 groups with 8,866,110 members around the world. It's a grassroots and entirely nonprofit movement of people who are giving (and getting) stuff for free in their own towns. It's all about reuse and keeping good stuff out of landfills. Each local group is moderated by local volunteers (them's good people). Membership is free
| Link to organisation | Edinburgh Freegle | https://groups.yahoo.com/neo/groups/EdinburghFreegle/info | Edinburgh Freegle, Don't throw it away, give it away! You might not want it, but someone just round the corner might. Items must be legal and appropriate, and free. Items can't be lent, swapped or sold
Travel | Link to organisation | Liftshare.co.uk | https://liftshare.co/uk | UK’s largest car share community
| Link to organisation | Traveline Scotland | http://www.travelinescotland.com/cms/content/Travelbybike.xhtml | This page provides guidance on which public transport operators offer a bike carrying facility
| Website for map | Edinburgh Bicycle innertube map | http://www.innertubemap.com/ | Edinburgh Bicycle innertube map
| Link to organisation | Sustrans | http://www.sustrans.org.uk/ | A leading UK charity enabling people to travel by foot, bike or public transport for more of the journeys we make every day
| Link to organisation | Spokes | http://www.spokes.org.uk/ | Spokes objectives: To promote* cycling, as part of a sustainable transport and access strategy, and to ensure that councils and government actively do the same. To publicise the benefits of cycling for the community and individuals – like walking, it is cheap, efficient, enjoyable, healthy, non-polluting and intrinsically safe
| Link to organisation | Cycling Scotland | http://www.cyclingscotland.org/ | Cycling Scotland is a registered charity (SC029760) and a company limited by guarantee. We receive funding from Transport Scotland to bring cycling out from the fringes of everyday life and into the mainstream. We aim to establish cycling as an acceptable, attractive and practical lifestyle option
Economy | Website for festival | Disruptive Innovation Festival (DIF) 2-20 November 2015 | https://www.thinkdif.co/ | The DIF brings together thought-leaders, entrepreneurs, businesses, makers, learners and doers to catalyse system-level change for a future economy. Over three weeks, using a mix of online and face to face events, participants have an abundance of opportunities to explore the economy through a different lens. We want to share all the ways you and our partners are challenging the linear ‘take make and dispose’ model of the economy, replacing it by a more prosperous regenerative and circular economy - is this the ultimate disruption? Examples of some of the broad themes that encompass this are: DESIGN INNOVATION SYSTEMS THINKING 21ST CENTURY SCIENCE MATERIALS AND ENERGY NEW BUSINESS MODELS ENTREPRENEURSHIP SHARING ECONOMY INTERNET OF THINGS
Climate | Link to event | Pole to Paris | http://poletoparis.com/#home | Pole to Paris is a public awareness campaign ahead of COP21. The campaign follows a team of environmental scientists as they travel – by bicycle and foot – from the Polar Regions to Paris.
Useful reading/ resources for Environmental Sustainability Team
| Edinburgh Napier University website | Event creation forms | http://staff.napier.ac.uk/services/corporateaffairs/exchange/Pages/Resources.aspx | Information included: Service request forms ¦ How-to guides ¦ Word and Powerpoint templates¦ Corporate publication downloads ¦ Videos ¦ Logos, brand tools and guidelines ¦ Image bank ¦ Outlook templates ¦ Institute sub-brand logos, brand tools and guidelines ¦Dealing with the press ¦ Web and digital comms ¦ Event organisation ¦ Photography data protection materials
| Sustainability Exchange EAUC website | MetMUnch case study | http://www.sustainabilityexchange.ac.uk/green_gown_awards_2014_student_engagement_manch | Great case study of successful student engagement at Manchester Metropolitan University through the group MetMUnch
| Link to Leeds University website | University of Leeds Sustainability Strategy | http://sustainability.leeds.ac.uk/sustainability-strategy/ | Example of a sustainability strategy
| Article | Higher education’s sustainability imperative: how to practically respond? | http://vehicleforasmallplanet.com/wp-content/uploads/2012/04/SustainabilityCU.pdf | The purpose of this paper is to describe four phases for how universities have addressed a sustainability agenda and offer specific lessons for how and where experiences on one campus, the University of Colorado Boulder, have been met with success and other challenges. The authors offer general reflections for executing university-wide sustainability initiatives with a central intent of illuminating central barriers against, and incentives for, a coordinated and integrated approach to campus sustainability.
| Article | Engaging higher education institutions in the challenge of sustainability: Sustainable transport as a catalyst for action | http://www.researchgate.net/publication/259138426_Engaging_higher_education_institutions_in_the_challenge_of_sustainability_Sustainable_transport_as_a_catalyst_for_action | Over the last decade, higher educational institutions (HEIs) have become more conscious of their performance on sustainability. For many, this has not been an easy transition. This article focuses on a case study of an Australian university program aimed at leveraging staff/student behavioural change and wider institutional change by starting with sustainable transport (ST) in a context where the case study university was coming from a low base on sustainability outside teaching activities. The case study research program aimed to (1) engage with internal and external stakeholders identified with barriers and facilitators to ST, (2) encourage more ST behaviours via explicit Travel Plan strategies and (3) utilize the project to embed ST policy and programs institutionally and act as a catalyst for more extensive and integrated sustainability performance across a multi-camps university. In terms of strategic choice of the case study, this project was the first under the State Government (of Victoria, Australia) HEI TravelSmart program to embrace both staff and students in a ‘whole of campus-community approach’ to sustainable transport. Engaging higher education institutions in the challenge of sustainability: Sustainable transport as a catalyst for action - ResearchGate. Available from: http://www.researchgate.net/publication/259138426_Engaging_higher_education_institutions_in_the_challenge_of_sustainability_Sustainable_transport_as_a_catalyst_for_action [accessed Oct 1, 2015].
http://england.lovefoodhatewaste.com/content/download-new-love-food-hate-waste-free-app

## 4.aEvents 2016-2017
| Event Planner 2016/2017 Academic Year |  | 2017-07-20
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | EVENT DURATION | time axis 2015-09-01 to 2016-09-29
Sept | Trimester 1
Sept | Freshers Fair and Inductions
Sept | eCycle launch
Sept | Rosh Hashanah (Jewish New Year)
Sept | Yom Kippur (Day of Atonement)
Sept | Eid al-Adha
Oct | Liftshare week
Oct | Energy Saving week
Oct | Muharram
Oct | Halloween
Nov | All Saints' Day
Nov | Bonfire night
Nov | European Week for Waste Reduction
Nov | Diwali
Nov | Remembrance Day
Nov/Dec | BHF collection
Nov | First Sunday of Advent
Nov | St Andrew’s Day
Dec | World AIDS Day
Dec | Assessment week
Dec | Hanukkah
Dec | Christmas holidays
Dec | Christmas switch off
Jan | Mawlid al-Nabi
Jan | eCycle mid-year Launch
Jan | Re-Freshers week
Jan | Inter Trimester Week
Jan | Trimester 2
Jan | NSS Survey time
Jan | Burns' Night
Feb | Go Green Week
Feb/March | Fairtrade Fortnight
Feb/March | Essential Cycle Skills
Feb/March | Essential Cycle Skills and Bike Maintenance
Feb | World Cancer Day
Feb | Valentine's Day
Feb | Shrove (Mardi Gras)
March | Pass it on week
Feb | Ash Wednesday
Feb | Chinese New Year
Feb | World Day of Social Justice
March | Zero Discrimination Day
March | St David’s Day
March | World Wildlife Day
March | Holi Day
March | International Women's Day
March | Earth Hour
March | St.Patrick's Day
March | International Day of Happiness
March | International Day for the Elimination of Racial Discrimination
March | World Water Day
March | Meat Free Week
March | Palm Sunday
April | Bowel cancer awareness month
April | Easter Break
April | John Muir Day
April | April Fools' Day
April | Good Friday
April | Passover
April | Easter Sunday
April | World Health Day
April | Addressing Anxiety- Disrupting Negative thoughts
April | St. George's Day
April | Assessment week
April | Allergy Awareness Week
May | May (Labour) Day
May | Beltane
May | Trimester 3
May | BHF clothing collection
May | Walk to work week
May | Active Travel Champion training
May | Basic Bicycle Maintenance
May | Clean Europe Day
May | Inter Trimester Week
May | Guided Bicycle Ride
May | Mental Health Awareness Week
June | Bright Green Business event
June | Global Sharing week
June | Shavuot (Hebrew Pentecost)
June | Slowfood week
June | Health Promotion Day
June | Student move-out from accommodation
June | Bike Week
June | World Environment Day
June | EU Sustainable energy week
June | Pentecost (Whitsunday)
June | World Oceans Day
June | The Queen’s Official Birthday
June | Diabetes Week
June | Flag Day
June | Men's health week
June | Communication Skills for Collaboration
June | First Day of Ramadan
June | Summer solstice
June | Recycling Week with Zero Waste Scotland
June | Catch the bus week
July | Eid al-Fitr
July | Information Overload - How to disconnect.
Aug | Assessment week
Aug | Strategies for Multigenerational caregiving
Aug | eCycle Launch
Please visit this page for the EMS reference numbers: http://staff.napier.ac.uk/services/facilities/sustainability/managementprogrammes/Pages/EnvironmentalManagementSystem.aspx

## 4.b Events 2017-2018
| Event Planner 2017/2018 Academic Year |  | 2017-07-20
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | EVENT DURATION | time axis 2015-09-01 to 2016-09-29
Sept | Trimester 1
Sept | Freshers Fair and Inductions
Sept | eCycle launch
Sept | Rosh Hashanah (Jewish New Year)
Sept | Yom Kippur (Day of Atonement)
Sept | Eid al-Adha
Oct | Liftshare week
Oct | Energy Saving week
Oct | Muharram
Oct | Halloween
Nov | All Saints' Day
Nov | Bonfire night
Nov | European Week for Waste Reduction
Nov | Diwali
Nov | Remembrance Day
Nov/Dec | BHF collection
Nov | First Sunday of Advent
Nov | St Andrew’s Day
Dec | World AIDS Day
Dec | Assessment week
Dec | Hanukkah
Dec | Christmas holidays
Dec | Christmas switch off
Jan | Mawlid al-Nabi
Jan | eCycle mid-year Launch
Jan | Re-Freshers week
Jan | Inter Trimester Week
Jan | Trimester 2
Jan | NSS Survey time
Jan | Burns' Night
Feb | Go Green Week
Feb/March | Fairtrade Fortnight
Feb/March | Essential Cycle Skills
Feb/March | Essential Cycle Skills and Bike Maintenance
Feb | World Cancer Day
Feb | Valentine's Day
Feb | Shrove (Mardi Gras)
March | Pass it on week
Feb | Ash Wednesday
Feb | Chinese New Year
Feb | World Day of Social Justice
March | Zero Discrimination Day
March | St David’s Day
March | World Wildlife Day
March | Holi Day
March | International Women's Day
March | Earth Hour
March | St.Patrick's Day
March | International Day of Happiness
March | International Day for the Elimination of Racial Discrimination
March | World Water Day
March | Meat Free Week
March | Palm Sunday
April | Bowel cancer awareness month
April | Easter Break
April | John Muir Day
April | April Fools' Day
April | Good Friday
April | Passover
April | Easter Sunday
April | World Health Day
April | Addressing Anxiety- Disrupting Negative thoughts
April | St. George's Day
April | Assessment week
April | Allergy Awareness Week
May | May (Labour) Day
May | Beltane
May | Trimester 3
May | BHF clothing collection
May | Walk to work week
May | Active Travel Champion training
May | Basic Bicycle Maintenance
May | Clean Europe Day
May | Inter Trimester Week
May | Guided Bicycle Ride
May | Mental Health Awareness Week
June | Bright Green Business event
June | Global Sharing week
June | Shavuot (Hebrew Pentecost)
June | Slowfood week
June | Health Promotion Day
June | Student move-out from accommodation
June | Bike Week
June | World Environment Day
June | EU Sustainable energy week
June | Pentecost (Whitsunday)
June | World Oceans Day
June | The Queen’s Official Birthday
June | Diabetes Week
June | Flag Day
June | Men's health week
June | Communication Skills for Collaboration
June | First Day of Ramadan
June | Summer solstice
June | Recycling Week with Zero Waste Scotland
June | Catch the bus week
July | Eid al-Fitr
July | Information Overload - How to disconnect.
Aug | Assessment week
Aug | Strategies for Multigenerational caregiving
Aug | eCycle Launch
Please visit this page for the EMS reference numbers: http://staff.napier.ac.uk/services/facilities/sustainability/managementprogrammes/Pages/EnvironmentalManagementSystem.aspx

## 5.a OLD Events 2014-2015
| Event Planner 2014/2015 Academic Year |  | 2017-07-20
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | EVENT DURATION | time axis 2014-09-01 to 2015-09-30
Sept | Trimester 1 |  |  | 2014-09-08 | 103 | bar: 2014-09-08 to 2014-12-20; 2015-04-25 to 2015-04-26; 2015-05-02 to 2015-05-03; 2015-05-09 to 2015-05-10; 2015-05-16 to 2015-05-19; 2015-05-23 to 2015-05-24; 2015-05-30 to 2015-05-31; 2015-06-06 to 2015-06-07; 2015-06-12 to 2015-06-13; 2015-06-20 to 2015-06-21
Sept | Cycle to work day 2014 |  |  | 2014-09-03 | 1
Sept | Freshers Fair and Inductions | 2014-09-02 | 4 | 2014-09-06 | 5
Sept | eCycle launch | 2014-09-02 | 4 | 2014-09-06 | 5
Sept | Rosh Hashanah (Jewish New Year) | 0 | 0 | 2014-09-14 | 1
Sept | Yom Kippur (Day of Atonement) | 0 | 0 | 2014-09-23 | 1
Sept | Eid al-Adha | 0 | 0 | 2014-09-24 | 1
Oct | Liftshare week |  |  | 2014-10-06 | 5
Oct | Pregnancy and Infant Loss Remembrance Day |  |  | 2014-10-15 | 1
Oct | Energy Saving week | 2014-10-06 | 14 | 2014-10-20 | 5
Oct | Muharram |  |  | 2014-10-25 | 1
Oct | Halloween |  |  | 2014-10-31 | 1
Oct | Halloween |  |  | 2014-10-31 | 1
Nov | All Saints' Day |  |  | 2014-11-01 | 1
Nov | Bonfire night |  |  | 2014-11-05 | 1
Nov | Remembrance Day |  |  | 2014-11-11 | 1
Nov | Diwali | 0 | 0 | 2014-11-11 | 1
Nov | UK Road Safety Week |  |  | 2014-11-17 | 8
Nov | European Week for Waste Reduction | 2014-11-10 | 12 | 2014-11-22 | 7
Nov | BHF collection | 2014-11-28 |  | 2014-11-28 | 24
Nov | St Andrew’s Day |  |  | 2014-11-30 | 1
Dec | World AIDS Day |  |  | 2014-12-01 | bar: 2015-04-25 to 2015-04-26; 2015-05-02 to 2015-05-03; 2015-05-09 to 2015-05-10; 2015-05-16 to 2015-05-19; 2015-05-23 to 2015-05-24; 2015-05-30 to 2015-05-31; 2015-06-06 to 2015-06-07; 2015-06-12 to 2015-06-13; 2015-06-20 to 2015-06-21
Nov | First Sunday of Advent | 0 | 0 | 2014-11-29 | 1
Dec | Christmas switch off |  |  | 2014-12-06 | 14
Dec | Assessment week |  |  | 2014-12-08 | 12 | bar: 2015-04-25 to 2015-04-26; 2015-05-02 to 2015-05-03; 2015-05-09 to 2015-05-10; 2015-05-16 to 2015-05-19; 2015-05-23 to 2015-05-24; 2015-05-30 to 2015-05-31; 2015-06-06 to 2015-06-07; 2015-06-12 to 2015-06-13; 2015-06-20 to 2015-06-21
Dec | Hanukkah | 0 | 0 | 6-14/12/14 | bar: 2015-04-25 to 2015-04-26; 2015-05-02 to 2015-05-03; 2015-05-09 to 2015-05-10; 2015-05-16 to 2015-05-19; 2015-05-23 to 2015-05-24; 2015-05-30 to 2015-05-31; 2015-06-06 to 2015-06-07; 2015-06-12 to 2015-06-13; 2015-06-20 to 2015-06-21
Dec | Christmas holidays |  |  | 2014-12-22 | 14
Jan | Mawlid al-Nabi | 0 | 0 | 2015-01-03
Jan | eCycle mid-year Launch | 2015-01-05 | 0 | 2015-01-05 | 1
Jan | Inter Trimester Week | 0 | 0 | 2015-01-05 | 6
Jan | Trimester 2 | 2015-01-12 | 117 | 2015-05-09 | 0
Jan | NSS Survey time | 0 | 0 | 2015-01-13 | 80
Jan | Martin Luther King Day | 0 | 0 | 2015-01-18 | 1
Jan | Burns' Night | 0 | 0 | 2015-01-24 | 1
Jan | Work from Home Week |  |  | 2015-01-19 | 7
Jan | Holocaust Memorial Day |  |  | 2015-01-27 | 1
Feb | World Cancer Day | 0 | 0 | 2015-02-04 | 1
Feb | Go Green Week | 2015-01-27 | 14 | 2015-02-09 | 7
Feb | Valentine's Day | 0 | 0 | 2015-02-14 | 1
Feb | Shrove (Mardi Gras) | 0 | 0 | 2015-02-17 | 1
Feb | Chinese New Year | 0 | 0 | 2015-02-19 | 1
Feb | World Day of Social Justice | 0 | 0 | 2015-02-20 | 1
Feb | International Mother Language Day | 0 | 0 | 2015-02-21 | 1
Feb | Fairtrade Fortnight | 2015-01-27 | 27 | 2015-02-23 | 14
Feb | Essential Cycle Skills and Bike Maintenance | 2015-01-27 | 29 | 2015-02-25 | 1
March | St David’s Day |  |  | 2015-03-01 | 1
March | Zero Discrimination Day |  |  | 2015-03-01 | 1
March | World Wildlife Day |  |  | 2015-03-03 | 1
March | Essential Cycle Skills | 2015-01-27 | 36 | 2015-03-04 | 1
March | Holi Day | 0 | 0 | 2015-03-06 | 1
March | Pass it on week | 2015-02-18 | 17 | 2015-03-07 | 8
March | International Women's Day |  |  | 2015-03-08 | 1
March | St.Patrick's Day | 0 | 0 | 2015-03-17 | 1
March | International Day of Happiness |  |  | 2015-03-20 | 1
March | International Day for the Elimination of Racial Discrimination |  |  | 2015-03-21 | 1
March | World Water Day |  |  | 2015-03-22 | 1
March | Meat Free Week |  |  | 2015-03-23 | 5
March | Earth Hour | 2015-03-16 | 12 | 2015-03-28 | 1
March | Palm Sunday | 0 | 0 | 2015-03-29 | 1
April | Bowel cancer awareness month |  |  | 2015-04-01 | 30
April | April Fools' Day |  |  | 2015-04-01 | 1
April | Easter Break |  |  | 2015-04-03 | 14
April | Easter Sunday |  |  | 2015-04-05 | 1
April | World Health Day |  |  | 2015-04-07 | 1
April | John Muir Day | 2015-04-01 | 17 | 2015-04-18 | 8
April | Addressing Anxiety- Disrupting Negative thoughts |  |  | 2015-04-21 | 1
April | St. George's Day |  |  | 2015-04-23 | 1
April | Assessment week | 0 | 0 | 2015-04-27 | 12
April | Allergy Awareness Week | 2015-04-28 | 6 | 2015-05-04 | 0
April | Good Friday | 0 | 0 | 2015-04-03 | 1
April | Passover | 0 | 0 | 2015-04-04 | 1
May | National Walking Month |  |  | 2015-05-01 | 31
May | May (Labour) Day |  |  | 2015-05-01 | 1 | bar: 2015-06-10 to 2015-06-11; 2015-06-17 to 2015-06-18
May | Beltane |  |  | 2015-05-01 | 1 | bar: 2015-06-10 to 2015-06-11; 2015-06-17 to 2015-06-18
May | BHF clothing collection |  |  | 2015-05-02 | 30 | bar: 2015-06-10 to 2015-06-11; 2015-06-17 to 2015-06-18
May | Clean Europe Day | 2015-05-08 | 2 | 2015-05-10 | 3
May | Inter Trimester Week | 0 | 0 | 2015-05-10 | 7
May | Walk to work week | 2015-05-04 | 7 | 2015-05-11 | 5
May | Green Office Week | 2015-05-04 | 7 | 2015-05-11 | 5
May | Trimester 3 |  |  | 2015-05-18 | 103
May | Mental Health Awareness Week |  |  | 2015-05-18 | 5
May | Active Travel Champion training | 2015-05-04 | 18 | 2015-05-22 | 1
May | Shavuot (Hebrew Pentecost) |  |  | 2015-05-24 | 1
May | Basic Bicycle Maintenance | 2015-05-04 | 24 | 2015-05-28 | 1
May | Health Promotion Day | 0 | 0 | 2015-05-27 | 1
May | Student move-out from accommodation | 2015-05-27 | 2 | 2015-05-29 | 1
May | Work Wise Week |  |  | 2015-05-31 | 6
May | National Commute Smart Week |  |  | 2014-05-31 | 7
June | Slowfood week | 2015-05-25 | 7 | 2015-06-01 | 7
June | Guided Bicycle Ride | 2015-05-11 | 24 | 2015-06-04 | 1
June | National Work from Home Day |  |  | 2015-06-05 | 1
June | World Environment Day |  |  | 2015-06-05 | 1
June | Global Sharing week | 2015-05-21 | 17 | 2015-06-07 | 6
June | World Oceans Day | 0 | 0 | 2015-06-08 | 1
June | Bright Green Business event | 2015-05-18 | 22 | 2015-06-09 | 1
June | Green Transport Week |  |  | 2015-06-13 | 8
June | Bike Week | 2015-05-30 | 14 | 2015-06-13 | 8
June | The Queen’s Official Birthday |  |  | 2015-06-13 | 1
June | Diabetes Week |  |  | 2015-06-14 | 5
June | Flag Day |  |  | 2015-06-14 | 1
June | EU Sustainable energy week | 2015-06-08 | 7 | 2015-06-15 | 5
June | National Ride to Work Week |  |  | 2015-06-15 | 5
June | Men's health week |  |  | 2015-06-15 | 5
June | Communication Skills for Collaboration | 0 | 0 | 2015-06-16 | 1
June | First Day of Ramadan | 0 | 0 | 2015-06-18 | 1
June | Summer solstice | 0 | 0 | 2015-06-21 | 1
June | Recycling Week with Zero Waste Scotland | 2015-06-08 | 14 | 2015-06-22 | 5
June | Catch the bus week | 2015-06-15 | 14 | 2015-06-29 | 7
July | Eid al-Fitr | 0 | 0 | 2015-07-17 | 1
July | Information Overload - How to disconnect. | 0 | 0 | 2015-07-21 | 1
Aug | Assessment week | 0 | 0 | 2015-08-17 | 12
Aug | Strategies for Multigenerational caregiving | 0 | 0 | 2015-08-18 | 1
Aug | eCycle Launch | 2015-09-01 | 4 | 2015-09-05 | 12
Please visit this page for the EMS reference numbers: http://staff.napier.ac.uk/services/facilities/sustainability/managementprogrammes/Pages/EnvironmentalManagementSystem.aspx
University wide (Bold, Arial, 12, University Red: PANTONE 200 C)
Global, UN (Bold, Arial, 12, Green)
European (Bold, Arial, 12, Blue)
National (UK/ Scotland) and Local (Edinburgh region) (Bold, Arial, 12, Orange)
Non Env Sust related (Italic, Arial 10, no colour)